The Promise You Can Track — Myanmar Logistics & Delivery Campaign

Logistics & Supply Chain · Myanmar (Yangon, Mandalay, the Yangon–Mandalay corridor) · Integrated B2B + B2C campaign — trust building and demand generation

ZYNTH · The Intelligence of Creativity · zynth.asia

1. CAMPAIGN OVERVIEW

Every logistics company in Myanmar advertises speed. None of them advertises

honesty. The result is a market where the customer assumes the delivery date is

optimistic, the merchant assumes the courier will lose something eventually, and

both plan around a promise they do not believe.

That disbelief is expensive. Merchants hold extra stock. Customers refuse

prepayment. Both cost the operator margin.

Objective. 4,000 new merchant accounts and a 22-point lift in delivery-promise

trust over 14 weeks, at a cost per acquired merchant at or below MMK 38,000.

Period. 14 weeks. Budget envelope. MMK 54,000,000.

The bet. Do not promise faster. Promise *accurately*, then publish the score.

The operator who is honest about a two-day delivery beats the one who claims one

day and misses.

Segment A — The Online Seller (primary revenue)

Demographics. 22–38, majority women, running a Facebook or TikTok shop —

fashion, cosmetics, phone accessories, home goods. 30–400 parcels a month.

Location. Yangon (Insein, Hlaing, Thingangyun), Mandalay, secondary towns.

Psychographics. Their reputation *is* the courier's performance. One lost

parcel becomes a public comment thread under their next post.

Behaviours. Compares couriers in seller Facebook groups. Switches after two

bad experiences. Chooses on COD remittance speed as much as delivery speed.

Pain points. Cash-on-delivery money released slowly; no proof of a failed

delivery attempt; customer blames *them*, not the courier; no way to check a

parcel without calling.

Media. Facebook seller groups (constant), TikTok 8–11 PM, Viber for support.

Segment B — The Receiving Customer

Demographics. 18–40, urban and peri-urban, buys online 2–6 times a month.

Psychographics. Assumes the delivery window is fiction. Plans their day

around a call that may not come.

Pain points. No real-time location; "out for delivery" for two days; rider

calls once and marks it failed; no compensation path when something breaks.

Media. Facebook, TikTok, Viber. Reads reviews before paying in advance.

Segment C — The Corporate Shipper (highest value)

Demographics. 30–50, operations or supply-chain manager at a distributor,

pharma company, FMCG brand or manufacturer. Contracts worth MMK 30–400M a year.

Psychographics. Buys on documentation and reliability, not price. Needs to

show their own board a service-level record.

Pain points. No SLA reporting; damage claims unresolved for months; no cold

chain visibility; cannot audit a partner they cannot see.

Media. Email, LinkedIn, industry associations, direct relationships.

3. COMPETITIVE LANDSCAPE

| Who | What they claim | The gap |
| --- | --- | --- |
| Large national couriers | "Fastest nationwide" | No published performance; trust is assumed, not proven |
| App-based delivery startups | Tech-forward, young brand | Thin coverage outside Yangon; unstable rider supply |
| Traditional freight / bus cargo | Cheap, familiar | No tracking, no accountability, no documentation |
| In-house merchant fleets | Full control | Cannot scale; expensive per parcel |

Nobody publishes their on-time rate. Nobody. The first operator to do it — and

survive the bad months — takes "trustworthy" out of the category permanently.

The big idea — "The Promise You Can Track" / "ခြေရာခံနိုင်တဲ့ ကတိ"

Two meanings, both true. You can track the parcel — and you can track whether we

kept our word, because we publish the number every month.

The campaign puts a public performance board at the centre: on-time rate,

average delivery time by route, COD remittance speed, damage rate, claims

resolved. Updated monthly. Good months and bad months.

Why this and not the obvious one. The obvious campaign is a rider smiling on

a motorbike with "Fast · Safe · Reliable" over it. Every competitor already runs

it, which is exactly why nobody believes it. A published number cannot be

claimed by a competitor who is not willing to publish theirs — and the ones who

are losing will not publish. The idea defends itself.

Brand positioning. The courier that tells you the truth before you ask.

Key messages.

"We publish our score." — the monthly board, misses included.

"Your money, the next morning." — COD remittance as a named, measured promise.

"Two attempts, both photographed." — proof of attempt, ending the blame argument.

"You can see it. So can your customer." — tracking the seller can forward.

Tone of voice. Direct, unglamorous, accountable. Burmese written first in

everyday register — this audience is not corporate. No superlatives; the numbers

do that work.

Hashtags. Primary `#ခြေရာခံနိုင်တဲ့ကတိ` · Secondary `#PromiseYouCanTrack` `#ZeroExcuseDelivery`

5. CHANNEL STRATEGY

| Channel | Role | Share |
| --- | --- | --- |
| Facebook | The performance board and the seller community — where merchants already compare couriers | 38% |
| TikTok | Rider-POV storytelling and the receiving-customer audience | 22% |
| Viber | Merchant onboarding and support; where the switch decision is made | 15% |
| On-ground | Market and township activation — signing merchants in person | 18% |
| LinkedIn + direct | Segment C only — SLA reporting, capability pack | 7% |

6. CONTENT PLAN

Pillars. The Score 30% · The Route 25% · The Rider 25% · The Seller 20%.

| Week | The Score | The Route | The Rider | The Seller |
| --- | --- | --- | --- | --- |
| 1–3 | Baseline board published | Corridor explainer films (2) | Rider day-in-the-life (2) | Onboarding walkthrough (2) |
| 4–7 | Month 1 board + a missed target | Rainy-season honesty film | Night sorting hub (1) | Seller switch stories (3) |
| 8–11 | Month 2 board | Mandalay corridor (2) | Rider training (1) | COD remittance proof (2) |
| 12–14 | Quarter board + what we fixed | Last-mile township (2) | Rider awards (1) | 100-seller milestone |

Sample draft — Facebook, Week 4 (Burmese first)

> ဒီလ ကျွန်တော်တို့ရဲ့ အချိန်မီပို့နိုင်မှုက ၈၇% ပါ။

> ကျွန်တော်တို့ ကတိပေးထားတာက ၉၂% ပါ။ မမီပါဘူး။

> အကြောင်းရင်းက မိုးရာသီမှာ မန္တလေးလမ်းကြောင်း နှေးသွားလို့ပါ။ လာမယ့်လမှာ ကားနှစ်စီး တိုးထားပါပြီ။

> နောက်လမှာ ဒီနံပါတ်ကို ပြန်တင်ပါမယ် — ကောင်းသည်ဖြစ်စေ မကောင်းသည်ဖြစ်စေ။

>

> *Our on-time rate this month was 87%. We promised 92%. We missed it. The

> Mandalay corridor slowed in the rains. We have added two vehicles. We will

> publish this number again next month — good or bad.*

Sample draft — TikTok, Week 6 (rider POV, 22s)

> Opens on a rider's handlebar view, 6:40 AM, no music. Text on screen:

> "၄၂ ခု။ တစ်ရက်။" (42 parcels. One day.) Cuts through the day — the traffic, the

> wrong address, the customer who does not answer, the second attempt at 7 PM

> that succeeds. Ends: "တစ်ခုမှ မပျောက်ပါဘူး။" (Not one lost.) No voiceover. The

> only sound is the street.

7. OUTREACH STRATEGY

| Tier | Who | Deliverable | Fee band (MMK) |
| --- | --- | --- | --- |
| Seller-community | 6 admins of large seller groups | Honest trial + published verdict | 550,000 each |
| Creator | 4 mid-tier TikTok creators | Rider ride-along content | 900,000 each |
| Merchant advocate | 12 existing merchants | Filmed switch story at their shop | Cost only |
| Corporate | 2 supply-chain association figures | Hub tour + assessment for Segment C | 1,500,000 each |

Seller-group admins are the highest-leverage voices in this category and are

almost never used properly — they will only endorse after a real trial, which is

exactly why their endorsement moves the market.

8. PAID MEDIA PLAN

| Platform | Objective | Budget (MMK) | Audience | Expected |
| --- | --- | --- | --- | --- |
| Facebook | Merchant lead generation | 8,500,000 | Online sellers, small-business admins; 20–40 | CPL 30,000–42,000 |
| Facebook | Reach — the score board | 4,000,000 | Broad urban 18–45, Yangon/Mandalay | CPM 3,200–4,600 |
| TikTok | Video views + brand | 5,500,000 | 18–35, shopping and delivery interests | CPV 45–80 |
| Viber | Merchant conversion | 2,500,000 | Business communities | CPM 4,000–5,800 |
| LinkedIn | Segment C | 2,000,000 | Ops/supply-chain titles, MM + regional | CPC 1,400–2,600 |
| **Total** |  | **22,500,000** |  |  |

Sequence: the score board runs first as reach for three weeks. It is what makes

the lead-generation creative credible in week 4 — running them together wastes

both.

9. ACTIVATION — THE SWITCH DESK

Six Switch Desks across 14 weeks: a two-person stand in high-density seller

markets (Mingalar Zay, Yuzana Plaza, Mandalay Zaycho) where a merchant can open

an account in eleven minutes, ship their first parcel free, and watch it move on

the tracking screen before they walk away.

Plus one Open Hub Night for Segment C: corporate shippers walk the sorting

hub at 10 PM, when it is busiest and least presentable. That is the point.

10. DETAILED BUDGET

| Line | Unit | Qty | Rate (MMK) | Total (MMK) |
| --- | --- | --- | --- | --- |
| Content production — crew | day | 14 | 780,000 | 10,920,000 |
| Editing + subtitling (MM/EN) | asset | 32 | 165,000 | 5,280,000 |
| Performance board — design + monthly build | month | 4 | 900,000 | 3,600,000 |
| Paid media (see §8) | — | — | — | 22,500,000 |
| Creator + community fees | — | — | — | 9,900,000 |
| Switch Desks | desk-day | 6 | 1,250,000 | 7,500,000 |
| Open Hub Night (Segment C) | event | 1 | 2,800,000 | 2,800,000 |
| Merchant onboarding kit (print + samples) | 1,000 kits | 1 | 3,100,000 | 3,100,000 |
| Campaign management (14 weeks) | month | 3.5 | 2,300,000 | 8,050,000 |
| **Subtotal** |  |  |  | **73,650,000** |
| Contingency 10% |  |  |  | 7,365,000 |
| **Cost base** |  |  |  | **81,015,000** |

11. TIMELINE

| Weeks | Phase | Milestones |
| --- | --- | --- |
| 1–2 | Baseline | Measure the real on-time rate. Build the board. First shoot. |
| 3 | Publish | Baseline score goes public — the campaign's opening move |
| 4–7 | Trust | Score reach campaign, rider films, Switch Desks 1–2 |
| 5 | Month 1 board | First honest miss published |
| 8–11 | Demand | Lead generation switches on, Switch Desks 3–4, Open Hub Night |
| 12–14 | Scale | Desks 5–6, quarter board, Segment C proposals issued |

12. KPIs & SUCCESS METRICS

| Metric | Target | Source |
| --- | --- | --- |
| New merchant accounts | 4,000 | Operator CRM |
| Cost per acquired merchant | ≤ MMK 38,000 | Spend ÷ activated accounts |
| Merchant activation (first parcel in 14 days) | ≥ 62% | Operator data |
| Delivery-promise trust lift | +22 points | Survey, week 1 vs week 14, n=400 |
| Score-board post reach | 2.4M cumulative | Meta |
| Segment C qualified opportunities | 12 | CRM |
| COD remittance satisfaction | ≥ 80% | Merchant survey |

The trust survey must run in week 1. Without the baseline the 22-point claim is

unprovable, and we will not report a lift we cannot evidence.

13. ROI PROJECTION

Average merchant: 45 parcels/month at MMK 2,600 contribution = MMK 117,000/month.

Retention after 12 months: 58%.

| Scenario | Merchants | Active at 12mo | Year-1 contribution (MMK) | Return on 113M |
| --- | --- | --- | --- | --- |
| Conservative | 2,600 | 1,300 | 1,825,000,000 | 16× |
| Base | 4,000 | 2,320 | 3,257,000,000 | 29× |
| Upside | 5,200 | 3,120 | 4,380,000,000 | 39× |

Logistics returns look extreme because the unit economics are recurring — a

merchant acquired once ships every month. The number to watch is not

acquisition, it is activation and retention, which is exactly what the honesty

strategy is built to protect. An acquired merchant who does not trust the

promise churns in month two and the ROI collapses.

14. RISK & MITIGATION

| Risk | Likelihood | Impact | Mitigation | Owner |
| --- | --- | --- | --- | --- |
| The real on-time rate is embarrassing | **High** | High | Measure in week 1 before committing. If below 80%, fix operations first — we will not publish a number that destroys trust. | ZYNTH + client COO |
| Competitor attacks a published miss | Medium | Medium | Publish the fix alongside the miss. The attack makes them look like they are hiding theirs. | ZYNTH |
| Rider supply cannot absorb new volume | Medium | High | Volume ramp modelled with ops; lead-gen throttled to capacity | Client ops |
| Rainy season degrades performance mid-campaign | **High** | Medium | Seasonal honesty built into the content plan from week 4 | ZYNTH |
| COD remittance slips, undermining a core promise | Medium | High | Do not run the remittance message until finance confirms the SLA | Client CFO |

15. ZYNTH FEE & PROFIT MODEL

| Line | MMK |
| --- | --- |
| Cost base (incl. contingency) | 81,015,000 |
| **Client investment at 40% margin** | **135,025,000** |
| ZYNTH gross margin | 54,010,000 (40.0%) |

Clears the 35% floor at the 40% target. 50% deposit on signature, 25% at week

7, 25% on the quarter report. Market FX. Vendor lines RFQ-based and reconciled at

actuals — underspend returns to the client.

Lower-budget version: drop two Switch Desks and the onboarding print run

(−MMK 5,600,000 cost base → 125,700,000 investment). We will not cut the

performance board or the measurement — they are the campaign.

16. WHY ZYNTH

This campaign only works if someone is willing to publish a bad month. Most

agencies will talk a client out of that in the first meeting, because a bad

number is uncomfortable and comfort is easier to sell. We think the discomfort

is the entire asset.

What we have actually produced: a 20-section fintech launch proposal with full

segmentation and scenario modelling; a premium launch event proposal with a

complete vendor and risk register; a manufacturing campaign built on the same

transparency mechanic; a spec product film to commercial sound standards; eight

3D stage and exhibition concepts.

What we do not claim: a logistics client. This would be our first, and we would

rather say so than invent a case study. What we bring is the method, the

production capacity to sustain 32 assets in 14 weeks, and the willingness to

hold the client to a number in public.

---

*ZYNTH — The Intelligence of Creativity · zynth.asia*

*Figures indicative, vendor lines subject to RFQ. Market FX. 50% deposit on signature.*

Prepared by ZYNTH. Figures are indicative and subject to vendor RFQ. Market FX applies. 50% deposit on signature.