The Village Gets the Report First — NGO & Social Impact Communications Campaign

NGO & Social Impact · Myanmar (programme areas) + Singapore / regional institutional donors · Integrated communications campaign — community accountability, donor confidence, volunteer and staff recruitment

ZYNTH · The Intelligence of Creativity · zynth.asia

1. CAMPAIGN OVERVIEW

Every NGO in Myanmar produces an annual report. It is written in English, laid

out for a donor, published on a website the beneficiaries do not read, and

distributed to people who were not there.

The community that lived the programme is the last to hear how it went — if they

hear at all. And the donor, reading a document produced by the organisation being

evaluated, quietly discounts it.

Both audiences are being under-served by the same habit.

Objective. Raise institutional donor confidence enough to convert 4 renewals

and 3 new multi-year commitments, lift qualified volunteer applications by 140%,

and establish community reporting as the organisation's signature practice — over

20 weeks.

Period. 20 weeks. Budget envelope. MMK 46,000,000 (~S$13,900).

The bet. An organisation that reports to the community *before* the donor is

making a claim about itself no press release can make — and it is the single

strongest thing a donor can be shown.

Segment A — The Institutional Donor / Programme Officer

Demographics. 30–50, programme or grants officer at an international

foundation, bilateral agency, regional CSR fund, or Singapore family office.

Decides or recommends on grants of USD 50k–2M.

Location. Singapore, Bangkok, Yangon country offices, remote.

Psychographics. Personally answerable for outcomes they cannot observe

directly. Reads dozens of near-identical reports. Deeply sceptical of

self-assessment and of numbers with no method attached.

Pain points. Cannot verify claimed impact; partners over-promise then

under-report; no view of what failed; due-diligence burden with weak evidence;

reputational exposure if a partner is later found to have overstated.

Media. Email, LinkedIn, sector convenings, peer referral. Reads long

documents when they contain something new.

Segment B — The Community / Programme Participant

Demographics. Adults 20–60 in programme townships; mixed literacy; often the

household decision-maker on participation.

Psychographics. Has seen organisations arrive, photograph, and leave. Judges

credibility by whether someone came back and explained.

Pain points. No idea what happened to the programme after it ended; no channel

to say it did not work; asked for data repeatedly and never shown the result.

Media. Facebook (mobile), Viber groups, community radio in some areas,

in-person meetings above all.

Segment C — The Volunteer / Prospective Staff

Demographics. 21–34, graduates and early-career, Yangon and Mandalay.

Psychographics. Wants meaningful work but has heard the sector described as

politically fraught and administratively hollow. Looking for evidence of rigour.

Pain points. Cannot tell serious organisations from performative ones; no

visibility of what the work actually involves day to day.

Media. Facebook, LinkedIn, TikTok, university networks.

Segment D — The Domestic Individual Donor

Demographics. 28–55, Myanmar professionals and business owners who give.

Pain points. "Where did the money go" is unanswered; prefers to give directly

to people they know rather than to an institution they cannot audit.

Media. Facebook, Viber, word of mouth.

3. COMPETITIVE LANDSCAPE

"Competition" here is for donor confidence and public trust, not market share.

| Who | How they communicate | The gap we take |
| --- | --- | --- |
| Large INGOs | Polished English annual reports, professional photography | Community never sees it; reads as institutional, not accountable |
| Local CSOs | Facebook activity updates, event photos | No method, no outcome measurement, no failure reporting |
| Direct-giving campaigns | Individual stories, emotional appeal, fast | Cannot demonstrate systemic outcome or sustained delivery |
| Corporate CSR arms | Brand-led, campaign-shaped | Short-horizon, rarely independently verified |

Nobody in this landscape reports to the community first. It costs little and it

is the one practice a competitor cannot adopt without genuinely changing how they

operate.

The big idea — "The Village Gets the Report First" / "အစီရင်ခံစာကို ရွာက အရင်ရမယ်"

Invert the reporting order. Every programme cycle closes with a community

report-back: the organisation returns to the township, in Burmese, in person,

and presents what was spent, what was achieved, what was missed, and what will

change. The community responds — on record. Only *then* does the donor report go

out, and it carries the community's response inside it.

The donor document stops being a self-assessment. It becomes a transcript.

Why this and not the obvious one. The obvious campaign is beneficiary

portraits, a hopeful score, and "Together We Can". Every organisation in the

sector runs it, which is precisely why a donor discounts it. Reporting to the

community first is a *behaviour*, not a message — it produces evidence as a

by-product, and an organisation unwilling to hear the response in public simply

cannot copy it.

Brand positioning. The organisation that answers to the people it serves,

before the people who fund it.

Key messages.

"The village hears it first." — the reporting order, stated plainly.

"Including what did not work." — a named failure in every cycle report.

"Here is the method." — measurement approach published alongside every number.

"Ask us on the record." — an open community question channel with published answers.

Tone of voice. Plain, accountable, unsentimental. Burmese written first,

English transcreated — for this campaign that is not only house rule but the

argument itself. No rescue framing, no beneficiaries described as passive, no

imagery that trades on distress.

Hashtags. Primary `#ရွာကအရင်သိရမယ်` · Secondary `#VillageFirstReport` `#AskUsOnTheRecord`

5. CHANNEL STRATEGY

| Channel | Role | Share |
| --- | --- | --- |
| In-community | The report-backs themselves — the campaign's substance, not its promotion | 30% |
| Facebook | Where Segments B and D live; Burmese-first reporting films | 26% |
| LinkedIn + email | Segment A donor channel — method notes, cycle reports | 18% |
| TikTok | Segment C recruitment — the work as it actually is | 12% |
| Convenings + PR | Sector credibility, peer referral into donor networks | 14% |

6. CONTENT PLAN

Pillars. The Report-Back 35% · The Method 25% · The Response 25% · The Work 15%.

| Week | The Report-Back | The Method | The Response | The Work |
| --- | --- | --- | --- | --- |
| 1–5 | Township 1 filmed, published (1) | "How we measure" explainer (2) | Community Q&A published (1) | Field-team day (2) |
| 6–10 | Township 2 (1) | "What we got wrong last cycle" (1) | Response to hard questions (2) | Recruitment films (2) |
| 11–15 | Township 3 (1) | Data-collection walkthrough (2) | Independent observer note (1) | Partner org feature (1) |
| 16–20 | Cycle report + donor pack | Full method annex published | Cumulative response log | Year-ahead commitments (1) |

Sample draft — Facebook, Week 6 (Burmese first)

> ပြီးခဲ့တဲ့လက ရေရရှိရေးအစီအစဉ်မှာ ရေတွင်း ၁၄ တွင်း တူးဖို့ ကတိပေးခဲ့ပါတယ်။

> ၁၁ တွင်း ပြီးပါပြီ။ ၃ တွင်း မပြီးသေးပါဘူး — မြေအောက်ကျောက်လွှာကြောင့်ပါ။

> ဒါကို ရွာလူကြီးတွေကို လွန်ခဲ့တဲ့ တနင်္လာနေ့မှာ ကိုယ်တိုင်သွားပြီး ရှင်းပြခဲ့ပါတယ်။

> သူတို့ရဲ့ အဖြေက ဒီမှာ ရှိပါတယ် — ဖြတ်တောက်ထားခြင်း မရှိပါဘူး။

>

> *Last month we committed to 14 wells in the water programme. Eleven are

> complete. Three are not — the rock layer. We went and explained this to the

> village committee in person last Monday. Their response is below, uncut.*

Sample draft — LinkedIn, Week 12 (Segment A)

> Our Q3 cycle report is attached. Section 4 is titled "What we did not achieve"

> and runs to two pages. Section 7 is the community's recorded response to

> Section 4, which we did not edit. The measurement annex explains every number's

> source, including the two we consider unreliable and why. We would rather you

> find our weaknesses in our own report than in someone else's evaluation.

7. OUTREACH STRATEGY

| Tier | Who | Deliverable | Fee band (MMK) |
| --- | --- | --- | --- |
| Sector authority | 2 respected sector figures | Observe a report-back, publish an honest assessment | 1,200,000 each |
| Academic | 1 university researcher | Independent review of the measurement method | 2,400,000 |
| Community | 8 community representatives | Speak on record at report-backs | Honorarium + costs only |
| Recruitment | 3 student-network voices (Segment C) | Field-day content | 500,000 each |

Community voices are never paid for endorsement — only honoraria and travel.

Paying for testimony would destroy the exact asset this campaign is building.

8. PAID MEDIA PLAN

| Platform | Objective | Budget (MMK) | Audience | Expected |
| --- | --- | --- | --- | --- |
| Facebook | Reach — report-back films | 5,500,000 | Programme townships + Yangon/Mandalay 25–55 | CPM 3,000–4,400 |
| Facebook | Domestic donor engagement | 3,000,000 | Interest: charity, community, giving; 30–55 | CPL 22,000–34,000 |
| TikTok | Recruitment (Segment C) | 2,500,000 | 21–32, students and early career | CPV 40–70 |
| LinkedIn | Donor + sector (Segment A) | 3,000,000 | Foundation, development, CSR titles; SG/TH/regional | CPC 1,600–3,000 |
| **Total** |  | **14,000,000** |  |  |

Deliberately modest. In this sector paid reach past a point starts to look like

overhead spent on self-promotion, which damages the very trust being built. The

budget sits mostly in the report-backs themselves.

9. ACTIVATION — THE REPORT-BACKS

Four community report-backs across 20 weeks, one per programme township.

Format, fixed and published in advance:

1. What we said we would do (10 min, Burmese, printed one-page handout)

2. What we spent (10 min, itemised, no aggregate hiding)

3. What we achieved and what we did not (20 min)

4. Open floor, recorded and published (40 min)

5. What changes next cycle, committed on the spot (10 min)

Plus one Donor Field Day — Segment A donors attend a report-back as

observers, not guests. They watch the open floor. Nothing is rehearsed for them.

10. DETAILED BUDGET

| Line | Unit | Qty | Rate (MMK) | Total (MMK) |
| --- | --- | --- | --- | --- |
| Report-back delivery (venue, travel, handouts, interpretation) | event | 4 | 1,650,000 | 6,600,000 |
| Content production — field crew | day | 12 | 720,000 | 8,640,000 |
| Editing + subtitling (MM/EN) | asset | 26 | 175,000 | 4,550,000 |
| Measurement method annex + independent review | pack | 1 | 3,800,000 | 3,800,000 |
| Paid media (see §8) | — | — | — | 14,000,000 |
| Authority, academic + recruitment fees | — | — | — | 7,300,000 |
| Community honoraria + travel | — | — | — | 2,200,000 |
| Donor Field Day | event | 1 | 2,400,000 | 2,400,000 |
| Cycle report design + production (MM/EN) | report | 1 | 2,900,000 | 2,900,000 |
| Campaign management (20 weeks) | month | 5 | 1,850,000 | 9,250,000 |
| **Subtotal** |  |  |  | **61,640,000** |
| Contingency 10% |  |  |  | 6,164,000 |
| **Cost base** |  |  |  | **67,804,000** |

11. TIMELINE

| Weeks | Phase | Milestones |
| --- | --- | --- |
| 1–3 | Method | Measurement annex drafted, independent reviewer engaged, baseline donor survey |
| 4–5 | Township 1 | First report-back delivered and filmed |
| 6–9 | Publish | Films live, method explainers, first failure published |
| 10 | Township 2 | Second report-back |
| 11–14 | Donor | Field Day, LinkedIn programme, renewal conversations open |
| 15 | Township 3 | Third report-back |
| 16–20 | Close | Township 4, cycle report with community response, donor pack issued |

12. KPIs & SUCCESS METRICS

| Metric | Target | Source |
| --- | --- | --- |
| Donor renewals secured | 4 | Grant agreements |
| New multi-year commitments | 3 | Signed agreements |
| Donor confidence score | +25 points | Donor survey, week 1 vs 20, n=30 |
| Community report-back attendance | 600 cumulative | Attendance records |
| Community "I know what happened" score | ≥ 75% | Post-event survey, programme townships |
| Qualified volunteer applications | +140% | Application system |
| Cycle report downloads (donor/sector) | 900 | Site analytics |
| Questions answered on record | 100% | Response log |

The last metric is the one that matters internally. A question asked in public

and not answered undoes the entire campaign.

13. ROI PROJECTION

This is not a revenue campaign; return is measured in funding secured and

retained. Average institutional grant: USD 180,000 over two years.

| Scenario | Renewals | New commitments | Funding secured (USD) | Return on ~S$34k |
| --- | --- | --- | --- | --- |
| Conservative | 3 | 1 | 720,000 | 15× |
| Base | 4 | 3 | 1,260,000 | 27× |
| Upside | 5 | 5 | 1,800,000 | 38× |

Stated carefully: these are funding outcomes influenced by communications, not

caused by them alone. Programme quality, existing relationships and donor cycles

drive most of the result. The honest claim is that this campaign removes the

verification doubt that currently slows or shrinks decisions — it does not

manufacture funding, and any agency telling you otherwise is selling you a

number.

14. RISK & MITIGATION

| Risk | Likelihood | Impact | Mitigation | Owner |
| --- | --- | --- | --- | --- |
| **Do no harm** — published material identifies individuals or locations in ways that create risk for participants | Medium | **Severe** | Protection review before every publication; no GPS, no identifying detail, no faces without informed consent recorded in Burmese; participants may withdraw at any time, including after publication. Any doubt means the asset is not published. | ZYNTH + client protection lead |
| Community response at open floor is severely critical | **High** | Medium | This is the design working, not failing. Publish it and publish the commitment made in response. Rehearsing the floor would forfeit the entire asset. | Client leadership |
| Organisation is not operationally ready to answer publicly | Medium | High | Week-1 readiness assessment. If the programme cannot survive an open floor, fix delivery before communications. We will not stage a report-back. | ZYNTH + client |
| Donor reads published failures as poor performance | Medium | Medium | Frame in the method annex from the first contact; brief donors before the first publication, never after | Client partnerships |
| Sensitive operating environment restricts filming | **High** | Medium | Audio-only and written formats pre-approved as substitutes; township selection reviewed with the protection lead | Client + ZYNTH |
| Staff capacity absorbed by report-back preparation | Medium | Medium | Format fixed and templated so cycle two costs a fraction of cycle one | ZYNTH |

15. ZYNTH FEE & PROFIT MODEL

| Line | MMK |
| --- | --- |
| Cost base (incl. contingency) | 67,804,000 |
| **Client investment at 35% margin** | **104,314,000** (~S$31,600) |
| ZYNTH gross margin | 36,510,000 (35.0%) |

Priced at the 35% floor, not the 40% target. This is a deliberate, recorded

exception: the client's funds are donor funds, and taking target margin on

restricted grant money is not a position we want to defend. The floor is the

floor — we do not go below it, because a campaign we cannot resource properly

helps nobody.

50% deposit on signature, 25% at week 10, 25% on the cycle report. Market FX.

Vendor lines RFQ-based, reconciled at actuals; underspend returns to the client.

16. WHY ZYNTH

This campaign asks an organisation to publish its failures and record the

criticism of the people it serves. Most agencies will steer a client away from

that within ten minutes, because comfortable work is easier to sell and easier to

approve. We are proposing it because in this sector the discomfort *is* the

credential — and because a donor who watches an unrehearsed open floor stops

needing to be convinced.

What we have actually produced: a 20-section fintech launch proposal with full

segmentation and scenario modelling; a premium launch event proposal with a

complete vendor and risk register; manufacturing, logistics and energy campaigns

built on the same published-evidence mechanic; a spec product film to commercial

sound standards; eight 3D stage and exhibition concepts.

What we do not claim: an NGO client, or field protection expertise. This would be

our first in the sector, and the protection review in §14 must be led by the

client's own safeguarding lead, not by us. What we bring is the method, the

bilingual production capacity, and a refusal to make the work look better than it

is.

---

*ZYNTH — The Intelligence of Creativity · zynth.asia*

*Figures indicative, vendor lines subject to RFQ. Market FX. Priced at the 35% margin floor by exception — donor-funded work.*

Prepared by ZYNTH. Figures are indicative and subject to vendor RFQ. Market FX applies. 50% deposit on signature.