EVENT PROPOSAL: WAVE PAY PREMIUM LAUNCH

Banking & Finance / Fintech (mobile wallet) · Myanmar (Yangon) · Premium product launch — event

ZYNTH · The Intelligence of Creativity · zynth.asia

1. EXECUTIVE SUMMARY

WavePay has revolutionized digital payments in Myanmar. Now, as the financial landscape evolves, there is a strategic opportunity to capture the high-value segment: young professionals, entrepreneurs, and SME owners in Yangon. This proposal outlines a comprehensive, high-impact product launch event for WavePay's new premium digital banking feature.

ZYNTH proposes "The Next Wave: Elevating Your Financial Future," an exclusive, tech-forward launch event designed to position WavePay Premium not just as a tool, but as a lifestyle enabler for Myanmar's ambitious professionals.

Set in the prestigious Crystal Ballroom at LOTTE Hotel Yangon, this event will host 250 carefully curated guests, including VIPs, key media, strategic partners, and high-net-worth individuals. The evening will blend immersive technology, elegant hospitality, and a powerful narrative of financial empowerment. From a futuristic LED tunnel entrance to a dramatic product reveal and high-level networking, every touchpoint is engineered to generate buzz, drive immediate premium user acquisition, and solidify WavePay's market leadership.

With a proposed budget of 105,000,000 MMK, ZYNTH will deliver an end-to-end, turnkey solution encompassing creative direction, technical production, vendor management, and seamless execution.

Theme: "The Next Wave: Elevating Your Financial Future"

The narrative centers on progression, sophistication, and seamless control. We are moving from basic transactions to wealth management and premium lifestyle integration.

Visual Identity

Color Palette: Deep Navy Blue (trust/finance), Metallic Gold (premium/wealth), and Electric Cyan (technology/future).

Typography: Sleek, modern sans-serif fonts with clean lines.

Imagery: Abstract fluid dynamics (representing the "wave" and seamless flow of money), glowing digital nodes, and high-end lifestyle photography.

Key Experience Moments

The Digital Gateway (Arrival): Guests enter through a custom-built LED tunnel displaying flowing, abstract data streams that react to their movement, symbolizing stepping into the future of finance.

The Premium Lounge (Pre-Event): A sophisticated networking space featuring a bespoke cocktail bar, interactive touch-tables demonstrating the app's new features, and ambient electronic-jazz fusion music.

The Reveal (Main Show): A high-energy, synchronized light and sound sequence leading into a cinematic 3D projection mapping on the main stage, culminating in the CEO's keynote and the official unveiling of the premium features.

The SME Success Panel: A short, impactful discussion featuring top Yangon entrepreneurs discussing how digital finance accelerates their business, providing social proof.

Mood & Style References

The aesthetic is "Futuristic Elegance." It should feel like a high-end tech keynote (think Apple or Tesla) merged with an exclusive VIP gala. Lighting is moody and architectural, utilizing sharp lasers and soft ambient glows. Materials include brushed metal, dark acrylics, and high-resolution LED surfaces.

3. EVENT DETAILS

| Category | Detail |
| --- | --- |
| Event Name | The Next Wave: WavePay Premium Launch |
| Proposed Date | Thursday, September 17, 2026 (Q3) |
| Time | 5:30 PM – 9:30 PM |
| Venue | Crystal Ballroom, LOTTE Hotel Yangon |
| Total Attendance | 250 Guests |
| Format | Premium Cocktail Reception & Keynote Presentation |

Attendance Breakdown

| Guest Category | Target Number | Description |
| --- | --- | --- |
| VIPs & Executives | 30 | WavePay C-Suite, Yoma Bank Executives, Regulatory Officials |
| Media & KOLs | 40 | Top tier tech/business journalists, financial influencers, lifestyle KOLs |
| Strategic Partners | 50 | Key merchants, corporate partners, telecom representatives |
| Target Users | 130 | Pre-selected SME owners, young professionals, high-net-worth individuals |

Load-in & Setup (Morning - Afternoon)

| Time | Duration | Segment | Owner | Notes |
| --- | --- | --- | --- | --- |
| 08:00 - 12:00 | 4 hrs | Venue Access & Main Production Load-in | Production Manager | Stage, LED, Sound, Lighting setup. |
| 12:00 - 14:00 | 2 hrs | Technical Setup & Calibration | Technical Director | Sound check, lighting focus, LED content sync. |
| 14:00 - 16:00 | 2 hrs | Decor & F&B Setup | Event Manager | Floral arrangements, catering stations, lounge setup. |
| 16:00 - 17:00 | 1 hr | Full Technical Rehearsal | Production Team | Run through all cues, presentations, and AV. |
| 17:00 - 17:30 | 30 min | Staff Briefing & Final Checks | Event Manager | Guest flow, registration, emergency procedures. |

Event (Evening)

| Time | Duration | Segment | Owner | Notes |
| --- | --- | --- | --- | --- |
| 17:30 - 18:00 | 30 min | Guest Arrival & Registration | Registration Team | LED tunnel experience, welcome drinks, networking in Premium Lounge. |
| 18:00 - 18:30 | 30 min | Welcome Reception & Networking | MC | Ambient music, canapés, interactive feature demos. |
| 18:30 - 18:45 | 15 min | Opening Remarks & Welcome Address | MC / WavePay Executive | Set the stage, build anticipation. |
| 18:45 - 19:15 | 30 min | Keynote & Product Reveal: "The Next Wave" | WavePay CEO | Cinematic 3D projection mapping, official launch of WavePay Premium. |
| 19:15 - 19:45 | 30 min | Panel Discussion: "SME Growth & Digital Finance" | Moderator & Panelists | Interactive Q&A, real-world applications. |
| 19:45 - 20:15 | 30 min | Interactive Product Demo & Q&A | WavePay Product Team | Live demonstration of key premium features. |
| 20:15 - 20:45 | 30 min | Entertainment: Futuristic Dance Performance | Choreographer | High-energy, visually stunning performance. |
| 20:45 - 21:15 | 30 min | Networking & Closing Remarks | MC | Further networking, call to action for premium sign-ups. |
| 21:15 - 21:30 | 15 min | Guest Departure | Event Manager | Distribution of premium welcome kits. |

Strike (Night)

| Time | Duration | Segment | Owner | Notes |
| --- | --- | --- | --- | --- |
| 21:30 - 00:30 | 3 hrs | Production Strike & Load-out | Production Manager | Dismantle stage, AV, lighting, decor. |
| 00:30 - 01:30 | 1 hr | Venue Clean-up & Handover | Venue Staff | Final inspection. |

Stage Dimensions & Materials

Main Stage: 10m (W) x 5m (D) x 1m (H) with a central thrust extending 3m into the audience.

Materials: High-gloss black acrylic finish for a sleek, reflective surface. Integrated LED strips along the edges for dynamic lighting effects.

Backdrop: Seamless 10m (W) x 4m (H) LED wall as the primary visual element.

3D Design Brief (Blender)

Main Stage: Model the stage structure with integrated LED strips.

LED Tunnel Entrance: A 5m long, 3m high, 2.5m wide curved LED tunnel with dynamic content capabilities.

Premium Lounge: Design a modular lounge area with modern furniture, interactive touch-tables, and a branded bar.

Product Reveal Mechanism: Conceptualize a dramatic reveal moment for the WavePay Premium logo/interface on the main LED screen, possibly involving a holographic effect or a physical element rising from the stage.

Lighting Design

Fixture Types:

Moving Head Spotlights (e.g., Robe Pointe, Clay Paky Sharpy): 12 units for dynamic beam effects, aerials, and gobos. Positioned on front and side trusses.

LED Wash Lights (e.g., Chauvet Rogue R2 Wash): 16 units for stage color washes and ambient lighting. Positioned on overhead trusses and floor.

Profile Spotlights (e.g., ETC Source Four LED Series 2): 4 units for key lighting on speakers and performers, ensuring clear visibility.

Laser Projectors (e.g., Pangolin FB4-controlled RGB lasers): 2 units for futuristic beam shows and atmospheric effects.

Effects: Sharp, angular beams in electric cyan and deep blue. Slow, elegant color transitions during networking. High-energy, synchronized light show during product reveal and entertainment segments.

Sound System Specs

Main PA System: Line array system (e.g., L-Acoustics K2 or d&b audiotechnik J-Series) suitable for the ballroom size, ensuring even coverage and clarity for speech and music.

Monitors: 4-6 stage monitors for speakers and performers.

Microphones: High-quality wireless handheld microphones (e.g., Shure ULXD series) for speakers and panel, lapel mics for key presenters.

Mixing Console: Digital mixing console (e.g., Yamaha CL5 or Avid S6L) with experienced sound engineer.

LED/Video Content Plan

Pre-Event: Dynamic abstract animations, WavePay branding, countdown timer.

Arrival: Interactive LED tunnel content reacting to guest movement.

Opening: High-definition WavePay corporate video, animated logo reveals.

Keynote: Custom-designed presentation slides, embedded video clips, live camera feed of speaker.

Product Reveal: Cinematic 3D animation showcasing WavePay Premium features, UI walkthroughs, holographic effects.

Panel Discussion: Branded lower-thirds, speaker profiles, live camera feed.

Entertainment: Synchronized visual content complementing the dance performance.

Networking: Ambient visuals, social media wall integration.

Special Effects

Haze Machines: 2-4 units for atmospheric enhancement of lighting beams.

Projection Mapping: Custom 3D projection mapping onto the main stage and surrounding architectural elements during the product reveal, creating an immersive environment.

Confetti Cannons: Discreetly placed for a celebratory burst during the peak product reveal moment.

6. VENDOR REQUIREMENTS

| Category | Recommended Vendor | Scope | Estimated Cost (MMK) | Lead Time | Backup |
| --- | --- | --- | --- | --- | --- |
| Stage Construction | Myanmar Event Management Co. (MEMC) | Design, fabrication, installation, and dismantle of main stage, LED tunnel, and lounge structures. | 20,000,000 | 4 weeks | iD Creative Solutions |
| Lighting | Light & Sound Myanmar | Supply, installation, programming, and operation of all lighting fixtures and effects. | 7,000,000 | 3 weeks | Pro Audio & Lighting |
| Sound | Pro Audio & Lighting | Supply, installation, calibration, and operation of main PA, monitors, microphones, and mixing console. | 4,000,000 | 3 weeks | Light & Sound Myanmar |
| LED Screens | Myanmar LED Solutions | Supply, installation, and operation of main LED wall and LED tunnel screens. | 8,000,000 | 3 weeks | Global LED Myanmar |
| Video Production | Yangon Film Services | Pre-event content creation (corporate video, animations), live camera operation, post-event highlight reel. | 4,000,000 | 6 weeks | Myanmar Motion Pictures |
| Photography | The Photo Studio Yangon | Event coverage, candid shots, VIP portraits, post-event editing. | 1,500,000 | 2 weeks | Myanmar Photography Group |
| MC | U Kyaw Kyaw (TBC) | Professional bilingual MC for event flow, introductions, and audience engagement. | 2,000,000 | 4 weeks | Daw Aye Aye (TBC) |
| DJ/Music | DJ Aura (TBC) | Ambient electronic-jazz fusion for reception, upbeat tracks for networking, specific cues for program. | 1,000,000 | 3 weeks | DJ Zay |
| Catering | LOTTE Hotel Yangon (In-house) | Premium canapés, finger foods, non-alcoholic beverages, bespoke cocktail bar. | 12,500,000 | 6 weeks | Chatrium Hotel Catering |
| Florist/Decor | Floral Art Myanmar | Stage floral arrangements, lounge decor, entrance accents. | 2,500,000 | 3 weeks | Yangon Flower Shop |
| Printing | Print Master Myanmar | Event signage, backdrop printing, VIP invitations, welcome kits. | 1,000,000 | 2 weeks | Express Print Yangon |
| Fabrication | Custom Props Myanmar | Custom interactive touch-tables, branded display elements. | 3,000,000 | 4 weeks | Event Decor & Props |
| Security | Venue Security (In-house) | Access control, crowd management, VIP protection. | 1,500,000 | 2 weeks | Private Security Services |
| Transport | Yangon Limousine Services | VIP transfers, talent transport, logistics support. | 1,000,000 | 2 weeks | Grab Business |

7. MARKETING & PROMOTION

ZYNTH will implement a targeted, multi-channel marketing and promotion strategy to maximize event attendance, media coverage, and brand engagement for WavePay Premium.

Pre-Event (6 Weeks Out)

| Week | Phase | Key Activities | Deliverables | Responsible Party |
| --- | --- | --- | --- | --- |
| Week 1-2 | Strategy & Content | Develop key messaging, visual assets, and content calendar. Identify target media and KOLs. | Event branding guidelines, press kit draft, social media content plan. | ZYNTH Marketing Team |
| Week 3 | Teaser Campaign | Launch cryptic social media teasers across WavePay and partner channels. Initiate direct outreach to VIPs and early-bird media. | Social media graphics, teaser video (15s), personalized VIP invitations. | ZYNTH Marketing Team, WavePay PR |
| Week 4 | Official Announcement | Issue press release to tech, business, and lifestyle media. Open limited registration for target users. | Official press release, event microsite/landing page, targeted digital ads. | ZYNTH Marketing Team, WavePay PR |
| Week 5-6 | Engagement & Outreach | Secure media interviews for WavePay executives. Partner with financial influencers for sponsored content. Send out final event details and reminders. | Media interview schedule, influencer content, event reminder emails/SMS. | ZYNTH Marketing Team, WavePay PR |

During-Event

| Activity | Description | Responsible Party |
| --- | --- | --- |
| Live Social Media Coverage | Real-time updates, stories, and posts across WavePay and ZYNTH channels. Encourage guest participation with a unique event hashtag. | ZYNTH Social Media Team |
| Media Relations Desk | Dedicated area for media check-in, press kit distribution, and interview scheduling. | WavePay PR Team |
| Professional Photography & Videography | Capture key moments, guest interactions, and product demonstrations for post-event use. | ZYNTH Production Team |
| Interactive Digital Displays | QR codes for immediate WavePay Premium sign-ups, social media wall displaying live posts. | ZYNTH Technical Team |

Post-Event (2 Weeks After)

| Week | Phase | Key Activities | Deliverables | Responsible Party |
| --- | --- | --- | --- | --- |
| Week 1 | Content Dissemination | Distribute event highlight video, photo gallery, and post-event press release. Share key takeaways and product benefits. | Highlight video (2-3 min), photo album, post-event press release. | ZYNTH Marketing Team, WavePay PR |
| Week 2 | Follow-up & Reporting | Send thank-you notes to attendees, media, and partners. Analyze media coverage and social media engagement. | Thank-you emails, media coverage report, social media analytics report. | ZYNTH Marketing Team |

8. BUDGET

Exchange Rate: 1 USD = 4,400 MMK

| Item | Description | Qty | Unit Cost (MMK) | Total (MMK) | Total (USD) |
| --- | --- | --- | --- | --- | --- |
| A. Venue & Hospitality |  |  |  | 20,000,000 | 4,545.45 |
| Ballroom Rental (Crystal Ballroom, LOTTE Hotel) | 5:00 PM - 10:00 PM (5 hours) | 1 | 15,000,000 | 15,000,000 | 3,409.09 |
| Hospitality Staff (Venue) | Ushers, cloakroom, general assistance | 10 | 100,000 | 1,000,000 | 227.27 |
| Cleaning & Security (Venue) | Post-event cleaning, additional security | 1 | 4,000,000 | 4,000,000 | 909.09 |
| B. Production & Technical |  |  |  | 48,500,000 | 11,022.73 |
| Stage Construction | Main stage, LED tunnel, lounge structures | 1 | 20,000,000 | 20,000,000 | 4,545.45 |
| Lighting Design & Equipment | Fixtures, programming, operation | 1 | 7,000,000 | 7,000,000 | 1,590.91 |
| Sound System & Engineering | PA, monitors, mics, mixing console | 1 | 4,000,000 | 4,000,000 | 909.09 |
| LED Screens & Content | Main LED wall, LED tunnel screens, content | 1 | 8,000,000 | 8,000,000 | 1,818.18 |
| Video Production | Pre-event content, live feed, post-event reel | 1 | 4,000,000 | 4,000,000 | 909.09 |
| Special Effects | Haze, projection mapping, confetti | 1 | 3,000,000 | 3,000,000 | 681.82 |
| Technical Crew | AV technicians, stagehands | 8 | 625,000 | 5,000,000 | 1,136.36 |
| C. Entertainment & Talent |  |  |  | 5,500,000 | 1,250.00 |
| MC Fee | Professional bilingual MC | 1 | 2,000,000 | 2,000,000 | 454.55 |
| DJ/Music | Ambient & event music | 1 | 1,000,000 | 1,000,000 | 227.27 |
| Dance Performance | Futuristic themed performance | 1 | 2,500,000 | 2,500,000 | 568.18 |
| D. Catering & F&B |  |  |  | 12,500,000 | 2,840.91 |
| Premium Canapés & Drinks | Per head catering for 250 guests | 250 | 50,000 | 12,500,000 | 2,840.91 |
| E. Marketing & Collateral |  |  |  | 5,000,000 | 1,136.36 |
| Photography | Event coverage, editing | 1 | 1,500,000 | 1,500,000 | 340.91 |
| Printing & Signage | Invitations, backdrops, branding | 1 | 1,000,000 | 1,000,000 | 227.27 |
| Fabrication (Interactive Displays) | Custom touch-tables, branded elements | 1 | 2,500,000 | 2,500,000 | 568.18 |
| F. Staffing & Management |  |  |  | 5,000,000 | 1,136.36 |
| Event Management Team (On-site) | ZYNTH team for coordination & execution | 5 | 1,000,000 | 5,000,000 | 1,136.36 |
| G. Transport & Logistics |  |  |  | 1,000,000 | 227.27 |
| VIP & Talent Transport | Limousine services, logistics support | 1 | 1,000,000 | 1,000,000 | 227.27 |
| Subtotal Project Cost |  |  |  | 99,500,000 | 22,613.64 |
| H. Contingency (10%) | Unforeseen expenses | 1 | 9,950,000 | 9,950,000 | 2,261.36 |
| Grand Total Project Cost |  |  |  | 109,450,000 | 24,875.00 |

9. ZYNTH PROFIT & COMMERCIAL MODEL

ZYNTH operates on a transparent commercial model, combining project management fees with a tiered pricing structure to offer flexibility and value to our clients.

| Item | Amount (MMK) | Amount (USD) |
| --- | --- | --- |
| Total Project Cost (excluding ZYNTH fee) | 109,450,000 | 24,875.00 |
| ZYNTH Management Fee (18% of Project Cost) | 19,699,000 | 4,477.05 |
| Total Client Price (Estimated) | 129,149,000 | 29,352.05 |
| ZYNTH Profit Margin (Estimated) | 19,699,000 | 4,477.05 |

Pricing Tiers for Future Engagements

ZYNTH offers flexible engagement models to suit varying client needs and project complexities.

| Tier | Description | Management Fee Percentage |
| --- | --- | --- |
| Lean | Basic event management, minimal creative input, focus on execution. | 10-12% |
| Standard | Comprehensive event management, moderate creative input, full vendor coordination. | 15-18% |
| Premium | Full-service, bespoke creative direction, extensive production, strategic marketing integration. | 20-25% |

10. TIMELINE & PROJECT PLAN

This timeline outlines the key phases and activities from project initiation to post-event wrap-up, spanning approximately 10 weeks.

| Week | Phase | Key Activities | Deliverables | Responsible Party |
| --- | --- | --- | --- | --- |
| Week 1 | Project Kick-off & Planning | Client brief deep dive, team allocation, initial concept refinement, venue confirmation. | Detailed project plan, confirmed venue booking, initial creative brief. | ZYNTH Project Lead, WavePay Marketing |
| Week 2 | Creative & Design Development | Finalize event concept, visual identity, stage design, and content themes. Vendor selection for key production elements. | Creative concept presentation, 3D stage renderings, vendor contracts (production). | ZYNTH Creative Director, Production Manager |
| Week 3 | Content & Technical Planning | Develop program flow, script keynotes, plan AV requirements, and content production schedule. | Detailed run of show, speaker scripts, AV technical rider, content production brief. | ZYNTH Event Manager, Technical Director |
| Week 4 | Marketing & Guest Management | Launch pre-event marketing campaign, finalize guest list, manage invitations and RSVPs. | Marketing campaign launch, guest list database, invitation management system. | ZYNTH Marketing Team, WavePay PR |
| Week 5 | Production & Fabrication | Begin fabrication of custom stage elements, LED tunnel, and interactive displays. Finalize catering and entertainment. | Production progress reports, catering menu, entertainment contracts. | ZYNTH Production Manager, Event Manager |
| Week 6 | Content Production & Rehearsals | Produce all video content, presentations, and digital assets. Schedule speaker rehearsals. | Final video content, presentation decks, rehearsal schedule. | ZYNTH Content Team, WavePay Speakers |
| Week 7 | Logistics & On-site Prep | Finalize all logistical arrangements, transport, staffing schedules. On-site technical checks. | Logistics plan, staff roster, preliminary AV tests. | ZYNTH Event Manager, Technical Director |
| Week 8 | Event Execution | Full event setup, technical rehearsals, guest management, live event execution. | Successful event delivery. | ZYNTH Full Team |
| Week 9 | Post-Event & Reporting | Venue strike, financial reconciliation, media monitoring, initial post-event report. | Financial summary, media coverage report, initial post-event analysis. | ZYNTH Project Lead, Finance |
| Week 10 | Final Deliverables & Review | Deliver final highlight video, photo gallery, and comprehensive event report. Client debrief. | Final event report, highlight video, photo gallery, client feedback session. | ZYNTH Project Lead |

11. KPIs & SUCCESS METRICS

Measuring the success of the WavePay Premium launch event is crucial. ZYNTH will track the following Key Performance Indicators (KPIs) to evaluate the event's effectiveness against its objectives.

| Metric | Target | Measurement Method |
| --- | --- | --- |
| Media Reach & Impressions | > 5,000,000 impressions | Media monitoring reports, social media analytics, press clipping analysis. |
| Social Media Engagement | > 1,000 mentions/shares of #WavePayPremiumLaunch | Social media analytics platforms (e.g., Facebook Insights, Twitter Analytics). |
| Event Attendance | 250 confirmed guests | Registration data, on-site check-in records. |
| Premium Feature Sign-ups (Immediate) | 10% of attendees sign up for WavePay Premium within 24 hours | WavePay internal data, unique QR code tracking at event. |
| Premium Feature Sign-ups (1-Month Post-Event) | 25% increase in WavePay Premium user base | WavePay internal data, comparison with pre-event baseline. |
| Brand Sentiment (Post-Event) | > 80% positive sentiment in media and social discussions | Sentiment analysis tools, qualitative review of media coverage. |
| Partner/VIP Satisfaction | > 90% satisfaction rating | Post-event survey for VIPs and partners. |
| Media Coverage Quality | > 10 high-tier media articles/features | Manual review of press clippings for key message inclusion and prominence. |
| Website/App Traffic (Premium Section) | > 20% increase in traffic to premium feature pages | Google Analytics, WavePay app analytics. |

12. RISK REGISTER

Effective risk management is integral to the successful execution of the WavePay Premium launch event. This register identifies potential risks, assesses their likelihood and impact, and outlines mitigation strategies.

| Risk | Likelihood (H/M/L) | Impact (H/M/L) | Mitigation |
| --- | --- | --- | --- |
| Venue Unavailability/Double Booking | L | H | Confirm booking with signed contract and deposit immediately. Have a secondary venue option (e.g., Novotel Yangon Max) on standby. |
| Key Speaker/Talent Cancellation | M | H | Secure backup speakers/talent. Draft clear contracts with cancellation clauses. Prepare contingency content (e.g., pre-recorded messages). |
| Technical Failures (AV, LED, Internet) | M | H | Redundant systems for critical AV components. On-site technical team for immediate troubleshooting. Pre-event full technical rehearsals. |
| Low Guest Attendance | M | M | Robust marketing and invitation strategy. Personalized follow-ups for VIPs. Engaging content to drive interest. |
| Negative Media Coverage/Social Media Backlash | L | H | Clear, consistent messaging. Proactive media relations. Crisis communication plan in place. |
| Budget Overruns | M | M | Strict budget tracking and regular reconciliation. Contingency fund (10%) for unforeseen expenses. |
| Weather-Related Disruptions | L | M | Indoor venue choice minimizes impact. Contingency plans for guest arrival/departure in heavy rain. |
| Vendor Non-Performance | M | M | Select reputable vendors with proven track records. Clear contracts with performance clauses. Backup vendors identified. |
| Product Demo Glitches | M | H | Thorough testing of product features. Multiple devices for demonstration. Backup presentation materials. |
| Security Breach/Crowd Control Issues | L | H | Professional security personnel. Clear entry/exit protocols. Emergency response plan. |
| Regulatory/Permit Issues | L | M | Early engagement with local authorities for all necessary permits and licenses. |
| Logistical Delays (e.g., customs for imported equipment) | M | M | Plan with ample lead time for all imported items. Work with experienced logistics partners. |

13. TERMS & CONDITIONS

This section outlines the standard terms and conditions governing the engagement between ZYNTH and WavePay for the "The Next Wave: WavePay Premium Launch" event.

Payment Terms

Deposit: A non-refundable deposit of 50% of the Total Client Price is required upon signing of this proposal to secure services and commence project activities.

Second Payment: 30% of the Total Client Price is due 4 weeks prior to the event date.

Final Payment: The remaining 20% of the Total Client Price is due within 7 days post-event, upon submission of the final event report and reconciliation.

All payments are to be made in Myanmar Kyat (MMK) via bank transfer.

Cancellation Policy

Cancellation by Client:

If cancelled 60 days or more prior to the event date, the 50% deposit will be forfeited.

If cancelled between 30-59 days prior to the event date, 75% of the Total Client Price will be payable.

If cancelled less than 30 days prior to the event date, 100% of the Total Client Price will be payable.

Cancellation by ZYNTH: In the unlikely event that ZYNTH must cancel the engagement, all payments made by WavePay will be fully refunded.

Force Majeure: Neither party shall be liable for any failure or delay in performing its obligations under this agreement if such failure or delay is caused by circumstances beyond its reasonable control, including but not limited to acts of God, war, terrorism, civil unrest, natural disasters, or government regulations.

Scope Boundaries

This proposal details the scope of work for the "The Next Wave: WavePay Premium Launch" event as described herein. Any additional services or significant changes to the scope requested by WavePay will be subject to a change order and may incur additional costs and adjustments to the timeline.

ZYNTH is responsible for the planning, coordination, and execution of the event as outlined. WavePay is responsible for providing timely approvals, necessary information, and access to relevant personnel and resources.

Client Responsibilities

Approvals: Timely review and approval of all creative concepts, production plans, budgets, and marketing materials.

Content: Provision of all necessary WavePay branding assets, product information, speaker content, and legal disclaimers.

Personnel: Availability of key WavePay personnel for meetings, rehearsals, and on-site support as required.

Decision Making: Prompt decision-making to avoid delays in the project timeline.

14. WHY ZYNTH

ZYNTH (zynth.asia) is a leading marketing and event management agency with a proven track record of delivering impactful and memorable experiences across Asia. Our commitment to innovation, meticulous execution, and strategic thinking makes us the ideal partner for WavePay's premium product launch.

Our Credentials

Regional Expertise: Deep understanding of the Myanmar market, cultural nuances, and logistical complexities, ensuring a locally relevant yet globally benchmarked event.

Creative Excellence: A portfolio of award-winning campaigns and events that push creative boundaries while achieving measurable business objectives.

Technical Proficiency: In-house expertise in cutting-edge event technology, including advanced AV, LED, projection mapping, and interactive installations.

Strategic Partnerships: Extensive network of trusted vendors and suppliers in Yangon, guaranteeing competitive pricing and reliable service.

Our Differentiators

Integrated Approach: We don't just execute; we integrate your marketing objectives into every aspect of the event, from concept to post-event follow-up.

Data-Driven Decisions: Our strategies are informed by market research and analytics, ensuring every investment yields maximum return.

Turnkey Solutions: From initial concept to final reporting, ZYNTH provides a seamless, single-point-of-contact experience, allowing WavePay to focus on its core business.

Agile & Responsive: Our team is equipped to adapt to evolving requirements and unforeseen challenges, ensuring a smooth and stress-free event delivery.

Our Team

Our dedicated team comprises experienced event strategists, creative directors, technical producers, and marketing specialists, all committed to bringing WavePay's vision to life. Led by a seasoned project manager, the ZYNTH team will work collaboratively with WavePay to ensure every detail is meticulously planned and flawlessly executed.

REFERENCES

[1] WavePay - App Store. (n.d.). Retrieved from https://apps.apple.com/us/app/wavepay/id1439175549

[2] WavePay APP by Wave Money. (2026, February 11). Retrieved from https://play.google.com/store/apps/details?id=mm.com.wavemoney.wavepay&hl=en_US

[3] Wave Money: Advancing Greater Financial Inclusion in Myanmar. (2021, February 17). The Digital Banker. Retrieved from https://thedigitalbanker.com/wave-money-advancing-greater-financial-inclusion-in-myanmar/

[4] Wave Money - Mobile Financial & Digital Payment in Myanmar. (n.d.). Retrieved from https://wavemoney.com.mm/

[5] WavePay - Finance App. (n.d.). Retrieved from https://mwm.ai/apps/wavepay/1439175549

[6] Wave Money and Yoma Bank Team up to Enable Seamless, Secure and Time-Saving Online Fund Transfer for WavePay and Yoma Bank Smart Account Holders. (2020, July 14). Yoma Bank. Retrieved from https://www.yomabank.com/en/news-and-activities/wave-money-and-yoma-bank-team-up-to-enable-seamless-secure-and-time-saving-online-fund-transfer-for-wavepay-and-yoma-bank-smart-account-holders/

[7] Chatrium Hotel Royal Lake Yangon. (2025, August 16). Facebook. Retrieved from https://www.facebook.com/ChatriumHotelRoyalLakeYangon/posts/%F0%9D%90%82%F0%9D%90%9E%F0%9D%90%A5%F0%9D%90%9E%F0%9D%90%9B%F0%9D%90%AB%F0%9D%90%9A%F0%9D%90%AD%F0%9D%90%A2%F0%9D%90%A8%F0%9D%90%A7%F0%9D%90%AC-%F0%9D%90%9A%F0%9D%90%AD-%F0%9D%90%82%F0%9D%90%A1%F0%9D%90%9A%F0%9D%90%AD%F0%9D%90%AB%F0%9D%90%A2%F0%9D%90%AE%F0%9D%90%A6-step-into-timeless-elegance-with-our-grand-ballroom-whe/1149254697233927/

[8] Melia Yangon Meetings and Events - Hotels. (n.d.). TravelAge West. Retrieved from https://www.travelagewest.com/Hotels/Yangon-Myanmar/Melia-Yangon/Meetings-Events-p52307395

[9] Sedona Hotel Yangon Meetings & Events. (n.d.). Business Travel News. Retrieved from https://www.businesstravelnews.com/Hotels/Yangon-Myanmar/Sedona-Hotel-Yangon/Meetings-Events-p50741012

[10] Event spaces - WEDDING & CONFERENCE. (n.d.). LOTTE HOTEL YANGON. Retrieved from https://www.lottehotel.com/yangon-hotel/en/wedding-convention/convention/overview

[11] Yangon, Myanmar Event Space & Hotel Conference Rooms. (n.d.). Northstar Meetings Group. Retrieved from https://www.northstarmeetingsgroup.com/Meeting-Event-Venues/Yangon-Myanmar/Hotels?pg=2

[12] Myanmar Event Management Company (MEMC). (n.d.). Myanmar Business Guide. Retrieved from https://www.mmbusinessguide.com/item/myanmar-event-management-company-memc/

[13] Myanmar's leading Event Organizers & Planners. (n.d.). GCA. Retrieved from https://www.gca.com.mm/blog/our-blog-1/7

[14] MEMC - Myanmar Event Management Company. (n.d.). Retrieved from https://memc.events/

[15] Who can provide services for an event in Yangon? (1 year ago). Facebook. Retrieved from https://www.facebook.com/groups/252698328960575/posts/1759901668240226/

Prepared by ZYNTH. Figures are indicative and subject to vendor RFQ. Market FX applies. 50% deposit on signature.