The Hours You Don't Lose — Myanmar Solar & Backup Power Campaign

Energy & Renewables (solar + backup power) · Myanmar (Yangon, Mandalay, Hlaing Tharyar & Shwe Pyi Thar industrial zones) · Integrated B2B + B2C campaign — demand generation and category education

ZYNTH · The Intelligence of Creativity · zynth.asia

1. CAMPAIGN OVERVIEW

Every solar company in Myanmar sells the same thing: a payback period. "Recover

your investment in 3.5 years." Buyers have heard it from six vendors, the numbers

never match, and the assumption underneath — that the grid stays as it is — is

the one thing nobody can promise.

So the buyer stalls. Not because solar is wrong, but because the argument is

unverifiable and everyone makes it.

This campaign changes the unit of measurement.

Objective. 180 qualified site surveys and 45 signed installations over 16

weeks, at a cost per qualified survey at or below MMK 95,000.

Period. 16 weeks. Budget envelope. MMK 68,000,000.

The bet. Nobody can verify a payback claim in advance. Everybody can count

the hours their business stopped last month. Sell the hours.

Segment A — The Factory / Workshop Owner (highest value)

Demographics. 35–58, owner or GM of a garment factory, cold store, printing

works, food processor or plastics plant. 40–600 staff. Diesel bill MMK 3–20M/month.

Location. Hlaing Tharyar, Shwe Pyi Thar, Mingaladon, Mandalay industrial belt.

Psychographics. Has been burned by an underspecified system that failed in

year two. Trusts the engineer who shows up, not the salesman who calls.

Behaviours. Asks other owners first. Wants to visit a working installation of

similar size before committing. Decides slowly, then buys fully.

Pain points. Production stops mid-shift; diesel cost and theft; generator

maintenance downtime; no way to compare vendor quotes because none use the same

assumptions; fear of being sold panels that underperform in monsoon.

Media. Viber business groups, Facebook, industry associations, WhatsApp with

their peers. Rarely searches; asks.

Segment B — The Commercial Building / Hotel Operator

Demographics. 30–50, GM or facilities head of a hotel, clinic, mall unit,

office building, private school.

Psychographics. Outages are a guest-experience problem before they are a cost

problem. A dark lobby is a review.

Pain points. Generator noise and fumes near guests; fuel logistics; peak

tariff exposure; no visibility on where power actually goes in the building.

Media. Facebook, LinkedIn, industry associations, direct sales relationships.

Segment C — The Household Buyer (volume, brand-building)

Demographics. 28–50, homeowner, dual-income, Yangon/Mandalay suburbs.

Psychographics. Wants the fridge, the fan, the wifi and the children's study

lamp to survive the cut. Not interested in kilowatts.

Pain points. Doesn't know what size to buy; afraid of being oversold; no

trusted installer; unclear warranty and who services it in year three.

Media. Facebook 8–10 PM, TikTok, YouTube for explainers, Viber for quotes.

3. COMPETITIVE LANDSCAPE

| Who | What they sell | The gap we take |
| --- | --- | --- |
| Established solar EPCs | Payback-period math, technical specs | Nobody can verify the claim before buying |
| Cheap import traders | Lowest price per panel | No design, no service, no accountability at year three |
| Generator suppliers | Familiarity, instant power | Fuel cost, noise, maintenance — the incumbent to displace |
| Regional/Chinese EPCs | Scale and price on large tenders | No local service depth, slow response |

Every player argues on price or specification. Nobody has claimed continuity

— the thing the buyer actually wants — and nobody publishes what their installed

systems delivered after the fact.

The big idea — "The Hours You Don't Lose" / "မဆုံးရှုံးတဲ့ နာရီများ"

Stop selling kilowatts. Stop selling payback. Sell the hours.

Every proposal, every ad, every case study is denominated in one number: the

hours this business kept running that it would otherwise have lost. A factory

does not experience 12 kWp. It experiences a shift that did not stop.

The campaign's engine is the Hours Counter — a published, per-installation

running total of outage hours covered, updated monthly from real inverter data

across the client's installed base. It is a number that only a company with real

installations can show, and it grows every month without new advertising.

Why this and not the obvious one. The obvious campaign is panels on a roof,

a sunrise, and "Power Your Future". It is interchangeable, it competes on price,

and it forces the payback argument the buyer has stopped believing. The Hours

Counter cannot be run by a trader with no installed base, cannot be faked, and

converts every past customer into ongoing proof.

Brand positioning. The power company that counts what you keep, not what you spend.

Key messages.

"Your last month, in hours." — a free outage audit that quantifies the loss.

"See it running." — visit a working installation your own size before you buy.

"Same assumptions, every quote." — a published quoting methodology so vendors can finally be compared.

"Year three is the test." — service record and warranty made the headline, not the footnote.

Tone of voice. Engineer-plain. Burmese first, everyday register for Segment C,

technical-professional for A and B. No sunrise language, no "green future"

abstraction — this market buys reliability, not sentiment.

Hashtags. Primary `#မဆုံးရှုံးတဲ့နာရီများ` · Secondary `#HoursYouDontLose` `#SeeItRunning`

5. CHANNEL STRATEGY

| Channel | Role | Share |
| --- | --- | --- |
| Facebook | The proof engine — Hours Counter, installation films, owner testimony | 34% |
| Viber | Segment A/B relationship channel — where factory owners actually talk | 18% |
| On-ground | Site-visit programme and two industry fairs — where the deal closes | 24% |
| TikTok / YouTube | Segment C education — "what size do I need" explainers | 14% |
| LinkedIn + direct | Segment B corporate and tender pipeline | 10% |

Segment A does not convert online. Digital's job is to earn the site visit; the

site visit closes.

6. CONTENT PLAN

Pillars. The Hours 30% · The Install 30% · The Owner 25% · The Answer 15%.

| Week | The Hours | The Install | The Owner | The Answer |
| --- | --- | --- | --- | --- |
| 1–4 | Counter launches with baseline | Factory install, full build film (2) | Garment factory owner (2) | "What size do I need" (3) |
| 5–8 | Month 1 hours total | Cold store install (2) | Hotel GM interview (1) | "How to compare 3 quotes" (2) |
| 9–12 | Month 2 + monsoon performance | Household install, one day (2) | Year-three customer (2) | "What breaks and who fixes it" (2) |
| 13–16 | Quarter total by sector | Mandalay industrial (2) | Diesel-vs-solar owner math (2) | Warranty explainer (1) |

Sample draft — Facebook, Week 5 (Segment A, Burmese first)

> ပြီးခဲ့တဲ့လမှာ ကျွန်တော်တို့ တပ်ဆင်ပေးထားတဲ့ စက်ရုံ ၄၁ ရုံအတွက်

> နာရီ ၂၂,၄၀၀ မီးပြတ်ချိန်ကို ဖြည့်ဆည်းပေးနိုင်ခဲ့ပါတယ်။

> ဒါက စက်ရုံတစ်ရုံကို ပျမ်းမျှ ၅၄၆ နာရီ — အလုပ်ရက် ၂၂ ရက်စာနီးပါးပါ။

> သင့်စက်ရုံ ပြီးခဲ့တဲ့လမှာ ဘယ်နှနာရီ ရပ်သွားလဲ သိပါသလား?

> အခမဲ့ စစ်ဆေးပေးပါတယ် — မေးလိုက်ရုံပါပဲ။

>

> *Last month our 41 installed factories covered 22,400 hours of outage — an

> average of 546 hours each, close to 22 working days. Do you know how many

> hours your factory stopped last month? We will audit it free.*

Sample draft — TikTok, Week 3 (Segment C, 28s)

> A woman opens her fridge during a cut. The light is on. No voiceover, no music.

> Text: "မီးပြတ်နေတာ ၄ နာရီရှိပြီ။" (The power has been out 4 hours.) She closes it,

> goes back to her daughter's homework under a working lamp. Final card:

> "မဆုံးရှုံးတဲ့ နာရီများ။" No panels are shown until the last two seconds.

7. OUTREACH STRATEGY

Technical credibility, not reach. Three tiers:

| Tier | Who | Deliverable | Fee band (MMK) |
| --- | --- | --- | --- |
| Authority | 2 engineering-association figures | Independent site inspection + published assessment | 2,000,000 each |
| Practitioner | 3 industrial/facilities voices | Installation walkthrough, Viber community post | 850,000 each |
| Customer | 10 existing installations | Filmed owner testimony at their own site | Cost only |
| Educator | 3 explainer creators (Segment C) | "What size do I need" series | 750,000 each |

The year-three customer is the single most persuasive asset in this category and

the one competitors cannot borrow — they either have those customers or they do not.

8. PAID MEDIA PLAN

| Platform | Objective | Budget (MMK) | Audience | Expected |
| --- | --- | --- | --- | --- |
| Facebook | Lead gen — free outage audit | 9,500,000 | Business owners/managers, manufacturing & hospitality interests, 30–58 | CPL 65,000–92,000 |
| Facebook | Reach — Hours Counter | 5,000,000 | Yangon/Mandalay industrial + suburban homeowners | CPM 3,400–4,800 |
| TikTok | Segment C education | 4,500,000 | 25–50, home & family interests | CPV 40–75 |
| Viber | Segment A/B communities | 3,500,000 | Business communities, industrial zones | CPM 4,200–6,000 |
| LinkedIn | Segment B corporate | 2,500,000 | Facilities/ops/GM titles, MM | CPC 1,300–2,500 |
| Search | High-intent capture | 2,000,000 | "solar factory Myanmar", "backup power" terms | CPC 900–1,900 |
| **Total** |  | **27,000,000** |  |  |

The free outage audit is the whole lead-gen mechanic. It costs the client an

engineer's afternoon and gives the buyer a number about their own business —

which is a far better hook than a discount.

9. ACTIVATION — SEE IT RUNNING

Six Site Visit Days across the campaign. Prospective buyers are taken to a

working installation of comparable size — a garment factory owner visits a

garment factory, not a showroom. They meet the owner without a salesperson in

the room, see the inverter data, and hear what went wrong during commissioning.

Plus presence at two industry fairs (Myanmar Energy Expo, Manufacturing

Myanmar) with a live load-shedding demonstration rig: the grid is cut on the

stand, every hour, and the stand stays lit.

10. DETAILED BUDGET

| Line | Unit | Qty | Rate (MMK) | Total (MMK) |
| --- | --- | --- | --- | --- |
| Content production — crew | day | 14 | 820,000 | 11,480,000 |
| Editing + subtitling (MM/EN) | asset | 30 | 195,000 | 5,850,000 |
| Hours Counter — data build + monthly publish | month | 4 | 1,150,000 | 4,600,000 |
| Paid media (see §8) | — | — | — | 27,000,000 |
| Authority, practitioner + educator fees | — | — | — | 8,800,000 |
| Site Visit Days | day | 6 | 1,450,000 | 8,700,000 |
| Industry fairs incl. demo rig | fair | 2 | 4,100,000 | 8,200,000 |
| Outage-audit toolkit (forms, app, training) | pack | 1 | 3,400,000 | 3,400,000 |
| Campaign management (16 weeks) | month | 4 | 2,450,000 | 9,800,000 |
| **Subtotal** |  |  |  | **87,830,000** |
| Contingency 10% |  |  |  | 8,783,000 |
| **Cost base** |  |  |  | **96,613,000** |

11. TIMELINE

| Weeks | Phase | Milestones |
| --- | --- | --- |
| 1–3 | Baseline | Inverter data pulled, Hours Counter built, audit toolkit trained, first shoot |
| 4 | Counter launch | Baseline hours published — the campaign's opening claim |
| 5–8 | Proof | Install films live, reach campaign, Site Visits 1–2, Fair 1 |
| 6 | Month 1 hours | First monthly total |
| 9–12 | Demand | Lead gen at full weight, Site Visits 3–4, monsoon performance published |
| 13–16 | Close | Site Visits 5–6, Fair 2, quarter total, Segment B tenders issued |

Monsoon falls inside this window. We publish monsoon performance rather than

avoid it — it is the objection every buyer raises and the one nobody answers.

12. KPIs & SUCCESS METRICS

| Metric | Target | Source |
| --- | --- | --- |
| Qualified site surveys | 180 | Client CRM |
| Cost per qualified survey | ≤ MMK 95,000 | Spend ÷ qualified surveys |
| Signed installations | 45 | Contracts |
| Survey-to-signature rate | ≥ 25% | CRM |
| Site Visit Day attendance | 150 cumulative | Registration |
| Segment C enquiries | 900 | Lead forms |
| Hours Counter reach | 3.1M cumulative | Meta |
| Brand association with "reliable" | +18 points | Survey week 1 vs 16, n=400 |

Baseline survey in week 1 or the final claim is unprovable. We will not report a

lift without it.

13. ROI PROJECTION

Average installation value: MMK 42,000,000 (blended across segments). Gross

margin to client: 26%.

| Scenario | Surveys | Close rate | Installs | Year-1 revenue (MMK) | Gross profit | Return on 135M |
| --- | --- | --- | --- | --- | --- | --- |
| Conservative | 135 | 20% | 27 | 1,134,000,000 | 294,840,000 | 2.2× |
| Base | 180 | 25% | 45 | 1,890,000,000 | 491,400,000 | 3.6× |
| Upside | 220 | 30% | 66 | 2,772,000,000 | 720,720,000 | 5.3× |

Return is stated on gross profit, not revenue — revenue multiples in a

high-ticket capital category flatter the number and mislead the decision. Even

the conservative case returns twice the investment inside year one, before any

service-contract annuity.

14. RISK & MITIGATION

| Risk | Likelihood | Impact | Mitigation | Owner |
| --- | --- | --- | --- | --- |
| Installed-base data too messy to publish | Medium | **High** | Week-1 data audit. If inverter data is not trustworthy, the Counter is delayed and the campaign leads on site visits instead. We will not publish an invented number. | ZYNTH + client engineering |
| Monsoon output undercuts the promise | **High** | Medium | Publish monsoon performance honestly with the design margin explained. It is the objection anyway. | ZYNTH |
| Sales team cannot absorb 180 surveys | Medium | High | Survey capacity agreed week 1; lead gen throttled to engineering headcount | Client sales |
| Free audit attracts unqualified enquiries | **High** | Medium | Qualification threshold (minimum monthly bill) set week 1; CPL reported on qualified only | ZYNTH |
| Price war triggered by competitor response | Medium | Medium | The campaign never argues price. If they cut, we publish year-three service records. | ZYNTH |
| Grid improves, weakening urgency | Low | Medium | Message pivots to tariff exposure and diesel cost, both unaffected | ZYNTH |

15. ZYNTH FEE & PROFIT MODEL

| Line | MMK |
| --- | --- |
| Cost base (incl. contingency) | 96,613,000 |
| **Client investment at 40% margin** | **161,022,000** |
| ZYNTH gross margin | 64,409,000 (40.0%) |

Clears the 35% floor at the 40% target. 50% deposit on signature, 25% at week

8, 25% on the quarter report. Market FX. Vendor lines RFQ-based, reconciled at

actuals; underspend returns to the client.

Reduced version: two fewer Site Visit Days and one fair (−MMK 7,000,000 cost base

→ 149,355,000 investment). We will not cut the Hours Counter or the outage-audit

toolkit — one is the campaign's proof and the other is its lead engine.

16. WHY ZYNTH

This campaign requires a client willing to publish real inverter data every

month, including the monsoon months. Most agencies will not propose that, because

if the data is bad the campaign gets harder. We propose it because if the data is

good it is unanswerable, and if the data is bad the client needs to know before

they spend 161 million on advertising around it.

What we have actually produced: a 20-section fintech launch proposal with full

segmentation and scenario modelling; a premium launch event proposal with a

complete vendor and risk register; manufacturing and logistics campaigns built on

the same published-evidence mechanic; a spec product film to commercial sound

standards; eight 3D stage and exhibition concepts.

What we do not claim: an energy client. This would be our first in the sector,

and we would rather say so than manufacture a case study. What we bring is the

method, the production capacity for 30 assets in 16 weeks, and a measurement

discipline that survives a bad month.

---

*ZYNTH — The Intelligence of Creativity · zynth.asia*

*Figures indicative, vendor lines subject to RFQ. Market FX. 50% deposit on signature.*

Prepared by ZYNTH. Figures are indicative and subject to vendor RFQ. Market FX applies. 50% deposit on signature.