You Will Understand Before You Decide — Myanmar Private Healthcare Campaign

Healthcare — private clinic or hospital group · Myanmar (Yangon, Mandalay) · Integrated trust campaign — patient confidence, first-visit conversion, retention

ZYNTH · The Intelligence of Creativity · zynth.asia

1. CAMPAIGN OVERVIEW

Private healthcare marketing in Myanmar competes on hardware. New scanner.

German equipment. Foreign-trained consultant. Every clinic runs the same

advertisement with a different machine in it.

Meanwhile the actual reason patients delay care, seek second opinions abroad, or

abandon a treatment plan is almost never the equipment. It is that nobody

explained it to them. They left the consultation with a prescription, a price,

and no understanding of what was decided or why.

That gap is a clinical problem before it is a marketing one — an unexplained plan

is an unfollowed plan.

Objective. Raise first-consultation-to-treatment-plan-acceptance by 11

points, lift 90-day follow-up attendance by 20%, and grow qualified new-patient

enquiries by 55% — over 18 weeks.

Period. 18 weeks. Budget envelope. MMK 64,000,000.

The bet. In a category shouting about machines, the clinic that promises

*understanding* is the one a frightened person chooses.

---

⚠️ Category discipline — read before anything else

This campaign makes no clinical outcome claims. No cure rates, no success

percentages, no comparative efficacy, no "best hospital", no patient outcome

implied or stated. Everything published is about process — how long we

explain, in what language, and whether the patient understood — never about

results.

Every asset passes a medical review gate before publication, signed by the

client's medical director. Patient stories require written informed consent in

Burmese, are anonymised by default, and may be withdrawn at any time including

after publication. No condition is named without explicit consent. No child

appears without guardian consent recorded on video.

If ZYNTH and the medical director disagree on whether an asset is safe to

publish, the medical director's decision is final and the asset is dropped.

---

Segment A — The Family Decision-Maker (primary)

Demographics. 30–52, usually the adult child or spouse arranging care for a

parent or partner. Household income MMK 1.5M+/month.

Location. Yangon (Bahan, Kamayut, Insein, South Okkalapa), Mandalay.

Psychographics. Carries the decision and the guilt. Terrified of choosing

wrong. Will spend more for confidence, not for comfort.

Behaviours. Asks family and colleagues first. Searches Facebook for the

clinic name plus complaints. Compares two or three, then commits fully.

Pain points. Consultations that last six minutes; medical Burmese they cannot

follow; a price quoted with no explanation of what is included; no idea what

happens if it does not work; the pull to send the patient to Bangkok instead.

Media. Facebook (all day, especially 8–11 PM), Viber family groups, YouTube

for explainers, direct phone.

Segment B — The Chronic-Condition Patient

Demographics. 45–70, managing diabetes, hypertension, kidney or cardiac

conditions. Returns or should return every 1–3 months.

Psychographics. Has drifted off the plan before. Stops attending when the

reason for attending stops being clear.

Pain points. Different doctor each visit; instructions that change without

explanation; cost accumulating with no visible progress; embarrassment about

asking again.

Media. Facebook, Viber, family relay, community networks.

Segment C — The Young Urban Preventive Patient

Demographics. 25–38, professionals, first-time private-healthcare buyers.

Psychographics. Health-literate, price-sensitive, sceptical of upselling.

Pain points. Suspects unnecessary tests; no transparent pricing; no idea what

a check-up should actually include.

Media. Facebook, TikTok, Google search, workplace referral.

Segment D — Clinical Staff (internal, non-negotiable)

Doctors and nurses are the campaign's delivery mechanism. A promise of

explanation that the consultation cannot honour is worse than no campaign at

all — it converts a marketing claim into a broken one, in person.

3. COMPETITIVE LANDSCAPE

| Who | What they claim | The gap we take |
| --- | --- | --- |
| Large private hospitals | Equipment, foreign-trained consultants, facilities | Impersonal, rushed, patients feel processed |
| Specialist clinics | Focused expertise, senior doctor's name | Little continuity, no patient education layer |
| Public hospitals | Cost, and genuine clinical depth | Queues, no time, no explanation |
| Bangkok / Singapore medical travel | Perceived certainty, service standard | Expensive, distant, family separated from the patient |

Nobody in this category has claimed comprehension. It is the cheapest thing to

deliver and the most valuable thing to receive, and it is sitting unowned.

The big idea — "You Will Understand Before You Decide" / "ဆုံးဖြတ်မယ့်အရင် နားလည်ပါစေ"

A promise about the consultation, not the outcome.

Every patient leaves with three things: the plan written in plain Burmese, the

cost itemised before consent, and — the part that changes everything — the

doctor asks the patient to explain the plan back in their own words before the

consultation ends. If they cannot, the doctor explains again. That is the standard.

We publish the one number that measures it: average explanation time per

consultation, by department, monthly. Not outcomes. Not success rates. Minutes

spent making sure someone understood.

Why this and not the obvious one. The obvious campaign is a scanner, a

smiling consultant, and "Advanced Care You Can Trust". It is what every

competitor runs, it is unverifiable, and it speaks to the machine rather than the

person deciding. A competitor cannot copy "understanding" without lengthening

their consultations — which costs them throughput, which is exactly why they will

not.

Brand positioning. The clinic that will not let you agree to something you do

not understand.

Key messages.

"Say it back to me." — the teach-back, named as the standard.

"The price before the consent." — itemised, in writing, in advance.

"In Burmese, on paper, to take home." — the plan leaves with the patient.

"Ask again. And again." — repeated questions framed as correct behaviour.

Tone of voice. Calm, plain, unhurried. Burmese written first — for this

campaign that is the argument, not a house rule. No white coats striding down

corridors, no dramatic music, no fear framing. Never imply that delay is the

patient's fault.

Hashtags. Primary `#နားလည်ပြီးမှဆုံးဖြတ်ပါ` · Secondary `#SayItBackToMe`

The internal move that makes it real

Before any spend: teach-back training for consulting staff, the plain-Burmese

plan template built and tested with real patients, itemised pricing implemented,

and explanation time measured for two weeks to establish a baseline. If the

consultation cannot deliver the promise, the campaign does not launch.

5. CHANNEL STRATEGY

| Channel | Role | Share |
| --- | --- | --- |
| Facebook | Where Segments A and B decide — explainer films, the monthly minutes, Q&A | 34% |
| In-clinic | The plan template, pricing sheets, waiting-room explainers — where the promise is kept | 20% |
| YouTube | Long-form condition explainers in Burmese, searchable, evergreen | 16% |
| Viber / CRM | Follow-up attendance — the retention engine for Segment B | 14% |
| TikTok | Segment C — short myth-correction, transparent pricing | 10% |
| Search + PR | High-intent capture and third-party credibility | 6% |

6. CONTENT PLAN

Pillars. The Explanation 35% · The Condition 25% · The Cost 20% · The Question 20%.

| Week | The Explanation | The Condition | The Cost | The Question |
| --- | --- | --- | --- | --- |
| 1–5 | Teach-back explained (2); baseline minutes published | Diabetes basics, Burmese (2) | "What a check-up includes" (1) | Ask-a-doctor round 1 (2) |
| 6–10 | Month 1 minutes by department | Hypertension (2); kidney care (1) | Itemised pricing explainer (1) | Round 2 (2) |
| 11–14 | Patient explains plan back, filmed with consent (2) | Cardiac follow-up (2) | "Why we did not order that test" (1) | Round 3 (2) |
| 15–18 | Quarter minutes + what changed | Preventive screening, Segment C (2) | Annual cost planning (1) | Round 4 + response log (1) |

Sample draft — Facebook, Week 6 (Burmese first)

> ပြီးခဲ့တဲ့လမှာ ကျွန်တော်တို့ရဲ့ ဆရာဝန်တွေဟာ လူနာတစ်ဦးကို ရှင်းပြဖို့

> ပျမ်းမျှ ၁၄ မိနစ် သုံးခဲ့ပါတယ်။

> ကျွန်တော်တို့ ကတိပေးထားတာက ၁၂ မိနစ်ပါ။

> အရေးကြီးဆုံးက မိနစ်အရေအတွက် မဟုတ်ပါဘူး — လူနာက ကိုယ့်စကားနဲ့ ပြန်ပြောပြနိုင်ဖို့ပါ။

> ပြန်မပြောနိုင်သေးရင် ထပ်ရှင်းပြပါတယ်။ ဒါက ကျွန်တော်တို့ရဲ့ စံပါ။

>

> *Last month our doctors spent an average of 14 minutes explaining to each

> patient. We commit to 12. The number that matters is not the minutes — it is

> whether the patient could say the plan back in their own words. If they could

> not, we explain again. That is our standard.*

Sample draft — TikTok, Week 4 (Segment C, 24s)

> A doctor, seated, straight to camera, no music: "ဒီစစ်ဆေးမှုက သင့်အတွက်

> မလိုအပ်ပါဘူး။" (You don't need this test.) Then thirty seconds on when it *is*

> needed and when it is simply being sold. Ends: "မလိုအပ်တာ မမှာပါဘူး။" (We don't

> order what isn't needed.) No branding until the final second.

7. OUTREACH STRATEGY

No paid patient testimonials. Ever. In this category a paid endorsement is a

regulatory and ethical problem before it is a credibility problem.

| Tier | Who | Deliverable | Fee band (MMK) |
| --- | --- | --- | --- |
| Clinical authority | 2 senior physicians (own staff) | Long-form Burmese condition explainers | Internal / honorarium |
| Independent | 1 medical association figure | Review of the teach-back protocol, published | 2,200,000 |
| Health educator | 3 credible health-content creators | Myth-correction series, script medically reviewed | 900,000 each |
| Patient voice | 10 patients | Consent-based story, **unpaid**, travel reimbursed only | Reimbursement only |

8. PAID MEDIA PLAN

| Platform | Objective | Budget (MMK) | Audience | Expected |
| --- | --- | --- | --- | --- |
| Facebook | Reach — explainers, minutes | 8,000,000 | 30–55, Yangon/Mandalay, family & health interests | CPM 3,200–4,600 |
| Facebook | Enquiry generation | 6,500,000 | Retargeting explainer viewers 50%+ | CPL 26,000–40,000 |
| YouTube | Long-form condition content | 4,000,000 | Search + suggested, Burmese health queries | CPV 55–110 |
| Viber | Segment B follow-up | 2,500,000 | Existing patient list, opted-in | — |
| TikTok | Segment C | 3,000,000 | 24–38, health & wellness | CPV 40–75 |
| Search | High intent | 2,500,000 | Condition + clinic terms | CPC 800–1,700 |
| **Total** |  | **26,500,000** |  |  |

No fear-based creative and no urgency mechanics. A frightened patient converts

worse and trusts less, and in healthcare that is a harm, not an inefficiency.

9. ACTIVATION — THE OPEN CONSULTATION HOUR

Twice monthly, at each site, a free Open Consultation Hour: no treatment, no

sales, no diagnosis. A doctor answers questions from anyone who walks in —

including "should I even be here" and "is this test necessary".

Nine sessions across the campaign. Deliberately non-converting by design; it is

the most literal possible demonstration of the promise, and it is where Segment A

decides.

Plus one Family Room session per month for Segment B: patients bring the family

member who actually manages their condition, and the plan is explained to both.

10. DETAILED BUDGET

| Line | Unit | Qty | Rate (MMK) | Total (MMK) |
| --- | --- | --- | --- | --- |
| Teach-back training + protocol design | programme | 1 | 4,200,000 | 4,200,000 |
| Plain-Burmese plan template (design, test, print) | build | 1 | 3,100,000 | 3,100,000 |
| Content production — crew | day | 13 | 790,000 | 10,270,000 |
| Editing + subtitling (MM/EN) | asset | 32 | 170,000 | 5,440,000 |
| Medical review gate (physician time) | month | 4.5 | 700,000 | 3,150,000 |
| Paid media (see §8) | — | — | — | 26,500,000 |
| Independent review + educator fees | — | — | — | 4,900,000 |
| Open Consultation Hours + Family Rooms | session | 13 | 480,000 | 6,240,000 |
| In-clinic materials, all sites | site | 5 | 540,000 | 2,700,000 |
| Campaign management (18 weeks) | month | 4.5 | 2,400,000 | 10,800,000 |
| **Subtotal** |  |  |  | **77,300,000** |
| Contingency 10% |  |  |  | 7,730,000 |
| **Cost base** |  |  |  | **85,030,000** |

11. TIMELINE

| Weeks | Phase | Milestones |
| --- | --- | --- |
| 1–3 | Make it true | Teach-back training, plan template tested with real patients, itemised pricing live, explanation-time baseline measured |
| 4 | Gate | Go / no-go. If consultations cannot honour the promise, we stop here. |
| 5–8 | Launch | Explainers live, baseline minutes published, Open Hours 1–2 |
| 9–12 | Depth | Month 1 minutes, condition library builds, Family Rooms, Viber follow-up engine |
| 13–15 | Proof | Teach-back filmed with consent, independent protocol review published |
| 16–18 | Close | Quarter minutes, response log, Segment C preventive push |

Week 4 is a real gate, not a formality. We have written it as a stopping point

because a broken promise in a consultation room costs more than the campaign.

12. KPIs & SUCCESS METRICS

| Metric | Target | Source |
| --- | --- | --- |
| Consultation-to-plan-acceptance | +11 points | Clinic system |
| 90-day follow-up attendance | +20% | Appointment records |
| Qualified new-patient enquiries | +55% | CRM |
| Average explanation time | ≥ 12 min sustained | Consultation logs |
| Teach-back completion rate | ≥ 85% of consultations | Clinical audit |
| Patient "I understood my plan" score | ≥ 88% | Exit survey, n≥500 |
| Open Consultation Hour attendance | 400 cumulative | Sign-in |
| Assets failing medical review | Reported, not hidden | Review log |

The last line is intentional. If nothing ever fails the medical gate, the gate is

not working, and we would rather show you the rejections.

13. ROI PROJECTION

Average treatment plan value: MMK 620,000. Baseline monthly first consultations:

1,400. Contribution margin 44%.

| Scenario | Acceptance lift | Incremental plans/mo | Year-1 contribution (MMK) | Return on 142M |
| --- | --- | --- | --- | --- |
| Conservative | +6 pts | 84 | 275,000,000 | 1.9× |
| Base | +11 pts | 154 | 504,000,000 | 3.5× |
| Upside | +15 pts | 210 | 687,000,000 | 4.8× |

Follow-up attendance is excluded from these figures despite being a target,

because attributing retention revenue to a communications campaign in an 18-week

window would overstate the case. It is upside we are choosing not to claim.

14. RISK & MITIGATION

| Risk | Likelihood | Impact | Mitigation | Owner |
| --- | --- | --- | --- | --- |
| **Clinical safety** — an asset is read as medical advice or an outcome promise | Medium | **Severe** | Medical review gate on every asset, signed by the medical director; no outcome claims anywhere; her decision is final and overrides ZYNTH | Client medical director |
| **Patient privacy** — a story identifies someone or their condition without full consent | Medium | **Severe** | Written Burmese consent, anonymised by default, withdrawal permitted after publication, no condition named without explicit consent, no child without guardian consent on video | Client + ZYNTH |
| Consultations cannot sustain 12 minutes at volume | **High** | High | Week 1–3 measurement, week 4 gate. Throughput modelling with clinic ops before launch. If it cannot hold, reduce scope to one department rather than break the promise everywhere. | Client ops |
| Published minutes fall below the commitment | Medium | Medium | Publish the miss and the cause, as with any honest measure | ZYNTH |
| Competitor claims the same language | Low | Low | They must lengthen consultations to deliver it. Throughput economics make this unattractive to them, which is the moat. | — |
| Staff experience the campaign as surveillance | Medium | High | Minutes reported at department level only, never individual; designed with staff in week 1, not imposed | Client HR |
| Open Hour attracts urgent cases needing real care | Medium | High | Triage protocol and referral path agreed before session 1 | Client clinical lead |

15. ZYNTH FEE & PROFIT MODEL

| Line | MMK |
| --- | --- |
| Cost base (incl. contingency) | 85,030,000 |
| **Client investment at 40% margin** | **141,717,000** |
| ZYNTH gross margin | 56,687,000 (40.0%) |

Clears the 35% floor at the 40% target. 50% deposit on signature, 25% at week

9, 25% on final report. Market FX. Vendor lines RFQ-based, reconciled at actuals;

underspend returns to the client.

Reduced version: three sites instead of five, six Open Hours instead of nine

(−MMK 2,520,000 cost base → 137,517,000). We will not cut the teach-back training,

the plan template or the medical review gate. The first two are what makes the

claim true; the third is what makes it safe.

16. WHY ZYNTH

This proposal contains a week-4 stopping point at which we recommend cancelling

our own campaign if the consultations cannot deliver what the advertising

promises. We have written it in because in healthcare a broken promise is not a

brand problem — it is a person who did not follow a treatment plan.

We have also declined the two easiest tools in this category: fear-based creative

and paid patient testimonials. Both work. Both are wrong here.

What we have actually produced: a 20-section fintech launch proposal with full

segmentation and scenario modelling; a premium launch event proposal with complete

vendor and risk registers; manufacturing, logistics, energy, NGO and F&B campaigns;

a spec product film to commercial sound standards; eight 3D stage and exhibition

concepts.

What we do not claim: a healthcare client, or clinical expertise. This would be

our first in the sector. Every clinical judgement in this campaign belongs to your

medical director, and the document is written so that her decision overrides ours

at every gate.

---

*ZYNTH — The Intelligence of Creativity · zynth.asia*

*No clinical outcome claims. All assets subject to medical review. Figures indicative, vendor lines subject to RFQ. Market FX. 50% deposit on signature.*

Prepared by ZYNTH. Figures are indicative and subject to vendor RFQ. Market FX applies. 50% deposit on signature.