ZYNTH  |  Myanmar-First Bilingual Production System

# Origin on the Table: Regional Ingredient Proof Pop-Up

မူရင်းကို စားပွဲပေါ်သို့ — ဒေသထွက်ပါဝင်ပစ္စည်း အတွေ့အကြုံပြပွဲ

CAMPAIGN / ACTIVATION PROPOSAL  •  CMP-2026-FNB-001  •  F&B / Myanmar

Client-ready planning proposal. All client, venue, chef, supplier, food-safety, product, claims, price, inventory, right, permit and partnership elements are proposed/TBC until written approval.

# 1. Commercial Brief

စီးပွားရေးဆိုင်ရာ အကျဉ်းချုပ်

| Format | Regional ingredient proof pop-up |
| --- | --- |
| Commercial tension | Consumers may enjoy a dish but lack a clear, non-exaggerated reason to choose it again when multiple F&B options feel interchangeable. |
| Objective | Convert taste curiosity into an opted-in tasting follow-up, product trial or client-approved purchase route. |
| Audience | Urban food-curious adults, local-product shoppers and invited hospitality/community stakeholders; exact audience and eligibility TBC. |
| Creative territory | The ingredient has a place, a season and a hand behind it. |
| Seasonal / date logic | Evergreen cultural-discovery format; use Q4 only if the client confirms a suitable product, venue and operating date. |

# 2. Conversion Experience

ပြောင်းလဲမှု အတွေ့အကြုံ

| Conversion mechanism | A three-station tasting card unlocks a QR ingredient/story card and a voluntary next-step preference selection; any order, delivery or purchase destination is client-approved/TBC. |
| --- | --- |
| Experience flow | Discover one regional ingredient → observe controlled preparation → taste a small labelled portion → select a preference → opt into a follow-up only with consent. |

# 3. Proposed Workplan

အဆိုပြုလုပ်ငန်းစဉ်

| Stage | Indicative timing | ZYNTH output | Client decision required |
| --- | --- | --- | --- |
| G0–G1: Brief & evidence | Working days 1–2 | Evidence register, audience hypothesis, claims boundary | Approve objective, data boundary and product facts |
| G2–G3: Strategy & creative | Working days 3–5 | Journey, creative route, content/experience plan | Select route and priority conversion action |
| G4: Feasibility | Working days 6–8 | Food safety, hygiene, venue, rights, staffing, consent and risk register | Name accountable owners and clear go/no-go conditions |
| G5: Production readiness | Working days 9–12 | Run-of-show, asset list, training, capture and escalation plan | Approve final assets, rules, terms and operations |
| G6–G7: Live & learn | Client/venue-confirmed | Dashboard check, daily log, decision record and learning note | Approve optimisation or close-out |

# 4. Budget Envelope

ဘတ်ဂျက် စီမံကိန်း

| Planning scenario | Non-tax envelope | Use |
| --- | --- | --- |
| Lean | MMK 12.5m | Minimum viable controlled pilot |
| Recommended | MMK 24.8m | Ingredient-story, controlled tasting, bilingual labelling, food-safety operations and data-capture led. |
| Flagship | MMK 48.5m | Expanded scale, content and operational capacity |

| Recommended budget workstream | Indicative share | Planning amount |
| --- | --- | --- |
| Strategy, creative & project direction | 15% | MMK 3.7m |
| Experience/production operations | 36% | MMK 8.9m |
| Staffing, training & facilitation | 18% | MMK 4.5m |
| Data, CRM & reporting | 8% | MMK 2.0m |
| Product/sampling/guest operations | 13% | MMK 3.2m |
| Contingency | 10% | MMK 2.5m |

# 5. Measurement and Commercial Scenarios

စောင့်ကြည့်တိုင်းတာမှုနှင့် Scenario

| Scenario | Directional outcome |
| --- | --- |
| Conservative | 90 completed tasting cards / 12 qualified follow-ups |
| Base | 180 completed tasting cards / 32 qualified follow-ups |
| Upside | 300 completed tasting cards / 60 qualified follow-ups |

| Primary KPIs | Labelled tasting completions; Consented preference selections; Qualified next-step requests; Approved product-trial redemptions |
| --- | --- |
| Data rule | Capture only client-approved, consented data needed for a stated follow-up; do not infer purchase intent, demographics or eligibility. |
| Scenario rule | Planning assumptions only. Replace with client funnel, margin, service capacity, inventory and attribution data before commercial sign-off. |

# 6. Mandatory Preflight

မဖြစ်မနေ အတည်ပြုရမည့်အချက်များ

Product/ingredient facts

Allergen and serving information

Food preparation and hygiene plan

Venue/permit

Consent text

Photography/rights

No health, safety, origin, sustainability, quality, availability, price, award, restaurant, chef or partnership claim may be used without written client/legal approval.

All third-party visual, music, talent, recipe, venue and photography rights must be cleared before production.

# 7. Evidence and Use Limits

အထောက်အထားနှင့် အသုံးပြုခွင့် ကန့်သတ်ချက်

| ID | Public source | URL |
| --- | --- | --- |
| FNB-S02 | Xinhua — Tastes of Golden Land | https://english.news.cn/20260726/49ff2f8a557b4825a58978e89ccccc61/c.html |
| FNB-S07 | Myanmar International TV — Tastes of the Golden Land | https://www.myanmaritv.com/news/tastes-golden-land-myanmar-traditional-food-competition-and-exhibition |
| FNB-S08 | Ministry of Information — Traditional Food Competition and Exhibition 2026 | https://www.moi.gov.mm/moi%3Aeng/news/21664 |
| FNB-S09 | Global New Light of Myanmar — Myanmar Urged to Cultivate Signature Foods | https://www.gnlm.com.mm/myanmar-urged-to-cultivate-signature-foods/ |

Evidence use: Sources provide public sector/event/calendar/compliance context only. They do not validate any future commercial partnership, venue, individual endorsement, performance, attendance or sales outcome.

Prepared by Manus AI for ZYNTH. Planning document only; not a contract, supplier quotation, legal advice or food-safety approval.