ZYNTH  |  Myanmar-First Bilingual Production System

# The Flavour Find: Guided Shelf-to-Sip Discovery Trail

အရသာရှာဖွေရေး — လမ်းညွှန်ထားသော Shelf-to-Sip Discovery Trail

CAMPAIGN / ACTIVATION PROPOSAL  •  CMP-2026-FNB-002  •  F&B / Myanmar

Client-ready planning proposal. All client, venue, chef, supplier, food-safety, product, claims, price, inventory, right, permit and partnership elements are proposed/TBC until written approval.

# 1. Commercial Brief

စီးပွားရေးဆိုင်ရာ အကျဉ်းချုပ်

| Format | Retail discovery trail |
| --- | --- |
| Commercial tension | New beverages or snack variants can be overlooked when choice overload makes shoppers default to familiar products. |
| Objective | Help a shopper identify one personally relevant flavour route and capture a consented re-engagement preference. |
| Audience | Client-defined retail visitors and adult beverage/snack shoppers; retail access and age/category rules TBC. |
| Creative territory | Do not browse the shelf. Follow your flavour. |
| Seasonal / date logic | Suitable for a non-holiday retail window; do not schedule around a public holiday without retailer confirmation. |

# 2. Conversion Experience

ပြောင်းလဲမှု အတွေ့အကြုံ

| Conversion mechanism | A five-question flavour card issues a route token to two or three client-approved discovery points, ending in a voluntary preference capture or offer reveal. |
| --- | --- |
| Experience flow | Choose a flavour mood → receive a route token → explore short product stories → sample only where approved → choose a preferred next step. |

# 3. Proposed Workplan

အဆိုပြုလုပ်ငန်းစဉ်

| Stage | Indicative timing | ZYNTH output | Client decision required |
| --- | --- | --- | --- |
| G0–G1: Brief & evidence | Working days 1–2 | Evidence register, audience hypothesis, claims boundary | Approve objective, data boundary and product facts |
| G2–G3: Strategy & creative | Working days 3–5 | Journey, creative route, content/experience plan | Select route and priority conversion action |
| G4: Feasibility | Working days 6–8 | Food safety, hygiene, venue, rights, staffing, consent and risk register | Name accountable owners and clear go/no-go conditions |
| G5: Production readiness | Working days 9–12 | Run-of-show, asset list, training, capture and escalation plan | Approve final assets, rules, terms and operations |
| G6–G7: Live & learn | Client/venue-confirmed | Dashboard check, daily log, decision record and learning note | Approve optimisation or close-out |

# 4. Budget Envelope

ဘတ်ဂျက် စီမံကိန်း

| Planning scenario | Non-tax envelope | Use |
| --- | --- | --- |
| Lean | MMK 10.8m | Minimum viable controlled pilot |
| Recommended | MMK 22.1m | Retail-routing, small-footprint display, trained guides, approved sampling and redemption instrumentation led. |
| Flagship | MMK 43.2m | Expanded scale, content and operational capacity |

| Recommended budget workstream | Indicative share | Planning amount |
| --- | --- | --- |
| Strategy, creative & project direction | 15% | MMK 3.3m |
| Experience/production operations | 36% | MMK 8.0m |
| Staffing, training & facilitation | 18% | MMK 4.0m |
| Data, CRM & reporting | 8% | MMK 1.8m |
| Product/sampling/guest operations | 13% | MMK 2.9m |
| Contingency | 10% | MMK 2.2m |

# 5. Measurement and Commercial Scenarios

စောင့်ကြည့်တိုင်းတာမှုနှင့် Scenario

| Scenario | Directional outcome |
| --- | --- |
| Conservative | 220 starts / 70 completions / 14 qualified opt-ins |
| Base | 460 starts / 180 completions / 42 qualified opt-ins |
| Upside | 800 starts / 340 completions / 84 qualified opt-ins |

| Primary KPIs | Route starts; Route completions; Preference captures; Client-approved offer redemptions |
| --- | --- |
| Data rule | Capture only client-approved, consented data needed for a stated follow-up; do not infer purchase intent, demographics or eligibility. |
| Scenario rule | Planning assumptions only. Replace with client funnel, margin, service capacity, inventory and attribution data before commercial sign-off. |

# 6. Mandatory Preflight

မဖြစ်မနေ အတည်ပြုရမည့်အချက်များ

Retailer access

Product availability

Any age/category controls

Offer terms

Sampling and hygiene plan

Data consent

No health, safety, origin, sustainability, quality, availability, price, award, restaurant, chef or partnership claim may be used without written client/legal approval.

All third-party visual, music, talent, recipe, venue and photography rights must be cleared before production.

# 7. Evidence and Use Limits

အထောက်အထားနှင့် အသုံးပြုခွင့် ကန့်သတ်ချက်

| ID | Public source | URL |
| --- | --- | --- |
| FNB-S01 | USDA Foreign Agricultural Service — Burma: Food Service - Hotel Restaurant Institutional | https://www.fas.usda.gov/data/gain/2025/02/burma-food-service-hotel-restaurant-institutional |
| FNB-S10 | Inter Myanmar Channel — Exploring HORECA 2026 Myanmar | https://www.youtube.com/watch?v=mbh1472c2HI |

Evidence use: Sources provide public sector/event/calendar/compliance context only. They do not validate any future commercial partnership, venue, individual endorsement, performance, attendance or sales outcome.

Prepared by Manus AI for ZYNTH. Planning document only; not a contract, supplier quotation, legal advice or food-safety approval.