ZYNTH  |  Myanmar-First Bilingual Production System

# One Dish, Many Hands: Open-Kitchen Craft Table

တစ်ပွဲတည်း၊ လက်များစွာ — Open-Kitchen Craft Table

CAMPAIGN / ACTIVATION PROPOSAL  •  CMP-2026-FNB-005  •  F&B / Myanmar

Client-ready planning proposal. All client, venue, chef, supplier, food-safety, product, claims, price, inventory, right, permit and partnership elements are proposed/TBC until written approval.

# 1. Commercial Brief

စီးပွားရေးဆိုင်ရာ အကျဉ်းချုပ်

| Format | Chef-led craft demonstration and preview |
| --- | --- |
| Commercial tension | A food brand may have a credible making process, yet customers see only the finished dish and cannot distinguish craft from generic promotion. |
| Objective | Create a high-attention, client-approved waitlist, tasting-session or content-consent pathway around visible craft. |
| Audience | Food-interested consumers, invited media/creators and client-defined guests; chef, venue and media participation TBC. |
| Creative territory | The making is part of the meal. |
| Seasonal / date logic | Proposed for late September or early October before the listed Thadingyut holidays; exact date TBC. |

# 2. Conversion Experience

ပြောင်းလဲမှု အတွေ့အကြုံ

| Conversion mechanism | A clearly timed demonstration ends with a question card, a controlled tasting sequence and an optional waitlist or session request. |
| --- | --- |
| Experience flow | Meet the dish story → observe selected preparation steps → ask a guided question → receive serving context → request a future client-approved seat or update. |

# 3. Proposed Workplan

အဆိုပြုလုပ်ငန်းစဉ်

| Stage | Indicative timing | ZYNTH output | Client decision required |
| --- | --- | --- | --- |
| G0–G1: Brief & evidence | Working days 1–2 | Evidence register, audience hypothesis, claims boundary | Approve objective, data boundary and product facts |
| G2–G3: Strategy & creative | Working days 3–5 | Journey, creative route, content/experience plan | Select route and priority conversion action |
| G4: Feasibility | Working days 6–8 | Food safety, hygiene, venue, rights, staffing, consent and risk register | Name accountable owners and clear go/no-go conditions |
| G5: Production readiness | Working days 9–12 | Run-of-show, asset list, training, capture and escalation plan | Approve final assets, rules, terms and operations |
| G6–G7: Live & learn | Client/venue-confirmed | Dashboard check, daily log, decision record and learning note | Approve optimisation or close-out |

# 4. Budget Envelope

ဘတ်ဂျက် စီမံကိန်း

| Planning scenario | Non-tax envelope | Use |
| --- | --- | --- |
| Lean | MMK 15.1m | Minimum viable controlled pilot |
| Recommended | MMK 31.2m | Open-kitchen staging, safety separation, demonstration talent, content rights and controlled guest-flow led. |
| Flagship | MMK 63.8m | Expanded scale, content and operational capacity |

| Recommended budget workstream | Indicative share | Planning amount |
| --- | --- | --- |
| Strategy, creative & project direction | 15% | MMK 4.7m |
| Experience/production operations | 36% | MMK 11.2m |
| Staffing, training & facilitation | 18% | MMK 5.6m |
| Data, CRM & reporting | 8% | MMK 2.5m |
| Product/sampling/guest operations | 13% | MMK 4.1m |
| Contingency | 10% | MMK 3.1m |

# 5. Measurement and Commercial Scenarios

စောင့်ကြည့်တိုင်းတာမှုနှင့် Scenario

| Scenario | Directional outcome |
| --- | --- |
| Conservative | 60 guests / 12 waitlist requests |
| Base | 140 guests / 36 waitlist requests |
| Upside | 260 guests / 78 waitlist requests |

| Primary KPIs | Seat/standing-zone attendance; Question-card submissions; Waitlist requests; Approved media/content opt-ins |
| --- | --- |
| Data rule | Capture only client-approved, consented data needed for a stated follow-up; do not infer purchase intent, demographics or eligibility. |
| Scenario rule | Planning assumptions only. Replace with client funnel, margin, service capacity, inventory and attribution data before commercial sign-off. |

# 6. Mandatory Preflight

မဖြစ်မနေ အတည်ပြုရမည့်အချက်များ

Chef/talent contract

Recipe/IP boundary

Food safety

Guest capacity

Content rights

Venue permissions

No health, safety, origin, sustainability, quality, availability, price, award, restaurant, chef or partnership claim may be used without written client/legal approval.

All third-party visual, music, talent, recipe, venue and photography rights must be cleared before production.

# 7. Evidence and Use Limits

အထောက်အထားနှင့် အသုံးပြုခွင့် ကန့်သတ်ချက်

| ID | Public source | URL |
| --- | --- | --- |
| FNB-S07 | Myanmar International TV — Tastes of the Golden Land | https://www.myanmaritv.com/news/tastes-golden-land-myanmar-traditional-food-competition-and-exhibition |
| FNB-S08 | Ministry of Information — Traditional Food Competition and Exhibition 2026 | https://www.moi.gov.mm/moi%3Aeng/news/21664 |
| FNB-S10 | Inter Myanmar Channel — Exploring HORECA 2026 Myanmar | https://www.youtube.com/watch?v=mbh1472c2HI |

Evidence use: Sources provide public sector/event/calendar/compliance context only. They do not validate any future commercial partnership, venue, individual endorsement, performance, attendance or sales outcome.

Prepared by Manus AI for ZYNTH. Planning document only; not a contract, supplier quotation, legal advice or food-safety approval.