ZYNTH  |  Myanmar-First Bilingual Production System

# A City of Small Tables: Neighbourhood Food Passport

စားပွဲငယ်များ၏ မြို့ — ရပ်ကွက်အစားအစာ Passport

CAMPAIGN / ACTIVATION PROPOSAL  •  CMP-2026-FNB-007  •  F&B / Myanmar

Client-ready planning proposal. All client, venue, chef, supplier, food-safety, product, claims, price, inventory, right, permit and partnership elements are proposed/TBC until written approval.

# 1. Commercial Brief

စီးပွားရေးဆိုင်ရာ အကျဉ်းချုပ်

| Format | Neighbourhood food-trail and local-business activation |
| --- | --- |
| Commercial tension | Independent food businesses may have distinct offers but little shared mechanism to help people discover, compare and return responsibly. |
| Objective | Generate transparent discovery, client-approved opt-in and measurable return routes without promising sales or partnership outcomes. |
| Audience | Client-approved adult visitors and participating local businesses; route, safety, access, partners and operating hours TBC. |
| Creative territory | A good city is remembered one small table at a time. |
| Seasonal / date logic | Proposed for November after the listed Tazaungdaing holidays; route and local-business confirmation required. |

# 2. Conversion Experience

ပြောင်းလဲမှု အတွေ့အကြုံ

| Conversion mechanism | A digital/print passport records client-approved visits or learning moments, then offers a voluntary preference capture and future route update. |
| --- | --- |
| Experience flow | Pick a route theme → receive rules/safety guidance → visit participating points → collect approved marks → reflect on a favourite → opt in to future routes. |

# 3. Proposed Workplan

အဆိုပြုလုပ်ငန်းစဉ်

| Stage | Indicative timing | ZYNTH output | Client decision required |
| --- | --- | --- | --- |
| G0–G1: Brief & evidence | Working days 1–2 | Evidence register, audience hypothesis, claims boundary | Approve objective, data boundary and product facts |
| G2–G3: Strategy & creative | Working days 3–5 | Journey, creative route, content/experience plan | Select route and priority conversion action |
| G4: Feasibility | Working days 6–8 | Food safety, hygiene, venue, rights, staffing, consent and risk register | Name accountable owners and clear go/no-go conditions |
| G5: Production readiness | Working days 9–12 | Run-of-show, asset list, training, capture and escalation plan | Approve final assets, rules, terms and operations |
| G6–G7: Live & learn | Client/venue-confirmed | Dashboard check, daily log, decision record and learning note | Approve optimisation or close-out |

# 4. Budget Envelope

ဘတ်ဂျက် စီမံကိန်း

| Planning scenario | Non-tax envelope | Use |
| --- | --- | --- |
| Lean | MMK 16.2m | Minimum viable controlled pilot |
| Recommended | MMK 33.8m | Route planning, local liaison, accessibility/safety communications, passport technology and field moderation led. |
| Flagship | MMK 69.2m | Expanded scale, content and operational capacity |

| Recommended budget workstream | Indicative share | Planning amount |
| --- | --- | --- |
| Strategy, creative & project direction | 15% | MMK 5.1m |
| Experience/production operations | 36% | MMK 12.2m |
| Staffing, training & facilitation | 18% | MMK 6.1m |
| Data, CRM & reporting | 8% | MMK 2.7m |
| Product/sampling/guest operations | 13% | MMK 4.4m |
| Contingency | 10% | MMK 3.4m |

# 5. Measurement and Commercial Scenarios

စောင့်ကြည့်တိုင်းတာမှုနှင့် Scenario

| Scenario | Directional outcome |
| --- | --- |
| Conservative | 110 activations / 38 route completions / 12 opt-ins |
| Base | 260 activations / 108 completions / 42 opt-ins |
| Upside | 500 activations / 230 completions / 98 opt-ins |

| Primary KPIs | Passport activations; Verified route completions; Consented preference captures; Client-approved return-route interest |
| --- | --- |
| Data rule | Capture only client-approved, consented data needed for a stated follow-up; do not infer purchase intent, demographics or eligibility. |
| Scenario rule | Planning assumptions only. Replace with client funnel, margin, service capacity, inventory and attribution data before commercial sign-off. |

# 6. Mandatory Preflight

မဖြစ်မနေ အတည်ပြုရမည့်အချက်များ

Participating businesses

Route safety/accessibility

Local permissions

Data consent

Photography

Crisis/contact plan

No health, safety, origin, sustainability, quality, availability, price, award, restaurant, chef or partnership claim may be used without written client/legal approval.

All third-party visual, music, talent, recipe, venue and photography rights must be cleared before production.

# 7. Evidence and Use Limits

အထောက်အထားနှင့် အသုံးပြုခွင့် ကန့်သတ်ချက်

| ID | Public source | URL |
| --- | --- | --- |
| FNB-S02 | Xinhua — Tastes of Golden Land | https://english.news.cn/20260726/49ff2f8a557b4825a58978e89ccccc61/c.html |
| FNB-S07 | Myanmar International TV — Tastes of the Golden Land | https://www.myanmaritv.com/news/tastes-golden-land-myanmar-traditional-food-competition-and-exhibition |
| FNB-S09 | Global New Light of Myanmar — Myanmar Urged to Cultivate Signature Foods | https://www.gnlm.com.mm/myanmar-urged-to-cultivate-signature-foods/ |

Evidence use: Sources provide public sector/event/calendar/compliance context only. They do not validate any future commercial partnership, venue, individual endorsement, performance, attendance or sales outcome.

Prepared by Manus AI for ZYNTH. Planning document only; not a contract, supplier quotation, legal advice or food-safety approval.