ZYNTH  |  Myanmar-First Bilingual Production System

# The Shared Tray: Hosted-Table Pre-Order Activation

မျှဝေစားပွဲ — Hosting Pre-Order Activation

CAMPAIGN / ACTIVATION PROPOSAL  •  CMP-2026-FNB-008  •  F&B / Myanmar

Client-ready planning proposal. All client, venue, chef, supplier, food-safety, product, claims, price, inventory, right, permit and partnership elements are proposed/TBC until written approval.

# 1. Commercial Brief

စီးပွားရေးဆိုင်ရာ အကျဉ်းချုပ်

| Format | Seasonal hosting pop-up and group-order conversion |
| --- | --- |
| Commercial tension | People planning a shared meal can lack confidence in what to order, how much to choose or how to coordinate a group without over-ordering. |
| Objective | Move hosting interest into a client-approved group-order consultation, menu-planning tool or pickup/delivery enquiry. |
| Audience | Client-defined households, office hosts and community organisers; service area and eligibility TBC. |
| Creative territory | The table begins with the people you are thinking of. |
| Seasonal / date logic | Proposed for the November–December hosting period while avoiding the listed 4 and 25 December dates unless operations are confirmed. |

# 2. Conversion Experience

ပြောင်းလဲမှု အတွေ့အကြုံ

| Conversion mechanism | A table-size planner creates a non-binding hosting card and offers an optional client-approved pre-order or consultation request. |
| --- | --- |
| Experience flow | Choose a gathering moment → set a table size → explore menu/serving prompts → build a non-binding card → request the next approved service step. |

# 3. Proposed Workplan

အဆိုပြုလုပ်ငန်းစဉ်

| Stage | Indicative timing | ZYNTH output | Client decision required |
| --- | --- | --- | --- |
| G0–G1: Brief & evidence | Working days 1–2 | Evidence register, audience hypothesis, claims boundary | Approve objective, data boundary and product facts |
| G2–G3: Strategy & creative | Working days 3–5 | Journey, creative route, content/experience plan | Select route and priority conversion action |
| G4: Feasibility | Working days 6–8 | Food safety, hygiene, venue, rights, staffing, consent and risk register | Name accountable owners and clear go/no-go conditions |
| G5: Production readiness | Working days 9–12 | Run-of-show, asset list, training, capture and escalation plan | Approve final assets, rules, terms and operations |
| G6–G7: Live & learn | Client/venue-confirmed | Dashboard check, daily log, decision record and learning note | Approve optimisation or close-out |

# 4. Budget Envelope

ဘတ်ဂျက် စီမံကိန်း

| Planning scenario | Non-tax envelope | Use |
| --- | --- | --- |
| Lean | MMK 11.9m | Minimum viable controlled pilot |
| Recommended | MMK 25.4m | Table-set design, planner UX, client-approved menu information, lead routing and service coordination led. |
| Flagship | MMK 52.8m | Expanded scale, content and operational capacity |

| Recommended budget workstream | Indicative share | Planning amount |
| --- | --- | --- |
| Strategy, creative & project direction | 15% | MMK 3.8m |
| Experience/production operations | 36% | MMK 9.1m |
| Staffing, training & facilitation | 18% | MMK 4.6m |
| Data, CRM & reporting | 8% | MMK 2.0m |
| Product/sampling/guest operations | 13% | MMK 3.3m |
| Contingency | 10% | MMK 2.5m |

# 5. Measurement and Commercial Scenarios

စောင့်ကြည့်တိုင်းတာမှုနှင့် Scenario

| Scenario | Directional outcome |
| --- | --- |
| Conservative | 100 planner completions / 14 enquiries |
| Base | 240 planner completions / 42 enquiries |
| Upside | 460 planner completions / 92 enquiries |

| Primary KPIs | Planner completions; Group-order enquiries; Consultation requests; Client-approved conversion rate |
| --- | --- |
| Data rule | Capture only client-approved, consented data needed for a stated follow-up; do not infer purchase intent, demographics or eligibility. |
| Scenario rule | Planning assumptions only. Replace with client funnel, margin, service capacity, inventory and attribution data before commercial sign-off. |

# 6. Mandatory Preflight

မဖြစ်မနေ အတည်ပြုရမည့်အချက်များ

Menu/allergen statements

Order rules

Service area

Capacity/inventory

Data consent

Holiday operating plan

No health, safety, origin, sustainability, quality, availability, price, award, restaurant, chef or partnership claim may be used without written client/legal approval.

All third-party visual, music, talent, recipe, venue and photography rights must be cleared before production.

# 7. Evidence and Use Limits

အထောက်အထားနှင့် အသုံးပြုခွင့် ကန့်သတ်ချက်

| ID | Public source | URL |
| --- | --- | --- |
| FNB-S04 | Myanmar Government — Upcoming Holidays | https://myanmar.gov.mm/upcoming-holidays |
| FNB-S05 | Myanmar eVisa — Public Holidays in Myanmar 2026 | https://evisa.moip.gov.mm/notice/public-holiday |
| FNB-S09 | Global New Light of Myanmar — Myanmar Urged to Cultivate Signature Foods | https://www.gnlm.com.mm/myanmar-urged-to-cultivate-signature-foods/ |

Evidence use: Sources provide public sector/event/calendar/compliance context only. They do not validate any future commercial partnership, venue, individual endorsement, performance, attendance or sales outcome.

Prepared by Manus AI for ZYNTH. Planning document only; not a contract, supplier quotation, legal advice or food-safety approval.