Built to be Trusted — Myanmar Manufacturing Sector Campaign

Manufacturing & Industrial · Myanmar (Yangon, Mandalay, Thilawa SEZ) · Integrated B2B campaign — brand authority + demand generation

ZYNTH · The Intelligence of Creativity · zynth.asia

1. CAMPAIGN OVERVIEW

Myanmar manufacturers sell on price because nobody has given buyers another

reason to choose. Procurement managers at distributors, hotel groups, and

construction firms compare quotes on a spreadsheet — and a spreadsheet only has

a column for cost. The manufacturer with the better factory loses to the one

with the lower number, and then both are squeezed again next quarter.

This campaign moves one manufacturer out of that column.

Objective. 120 qualified inbound enquiries and 25 factory visits over 16

weeks, at a cost per qualified lead at or below MMK 45,000 — against a

Yangon B2B outbound benchmark of roughly MMK 110,000 per meeting.

Period. 16 weeks. Budget envelope. MMK 62,000,000.

The bet. In a market where every competitor claims quality, the one who

*shows* it wins. Not a slogan — an open factory.

Segment A — The Procurement Manager

Demographics. 30–45, mixed gender, mid-senior at a distributor, hotel group,

construction firm or FMCG brand. Signs or shortlists for MMK 20–500M annually.

Location. Yangon (Downtown, Bahan), Mandalay industrial belt.

Psychographics. Personally accountable for a failure nobody remembers when

it goes right. Will pay 8–12% more for a supplier who will not embarrass them.

Behaviours. Researches on Facebook and Viber, decides in person. Asks peers

before asking Google. Wants a factory visit before a first order.

Pain points. Late delivery with no warning; inconsistent batch quality; no

documentation for their own auditors; suppliers who vanish when a defect appears.

Media. Facebook 8–10 PM, Viber business groups all day, LinkedIn rarely,

industry WhatsApp groups constantly. Trade press: Myanmar Business Today.

Segment B — The Factory Owner / Managing Director

Demographics. 40–60, owner-operator, 50–400 staff, second generation common.

Psychographics. Proud of the plant, frustrated it is invisible. Believes

marketing is for consumer brands and has been sold three websites that did nothing.

Pain points. Losing tenders to cheaper, worse competitors; no way to prove

capability without a site visit; every enquiry arrives through a personal contact.

Media. Facebook, Viber, chamber-of-commerce events, WhatsApp.

Segment C — The International Sourcing Agent

Demographics. 28–45, based Singapore/Bangkok, sourcing for regional buyers.

Psychographics. Risk-averse on Myanmar. Needs evidence of compliance,

capacity and continuity before recommending a supplier upward.

Pain points. Cannot verify claims remotely; no English documentation;

unclear certifications; no idea if the factory can hold volume.

Media. LinkedIn, email, industry directories, video walkthroughs.

3. COMPETITIVE LANDSCAPE

Myanmar industrial marketing is close to a vacuum, which is the opportunity.

| Who | What they do now | The gap we take |
| --- | --- | --- |
| Local manufacturers | A Facebook page with product photos, updated rarely | No proof, no process, no people |
| Regional importers (Thai, Chinese) | Polished catalogues, real certifications | Long lead times, no local service, no relationship |
| Trading intermediaries | Own the buyer relationship, hide the factory | We put the factory in front of the buyer directly |

Nobody in this category is publishing evidence. The first manufacturer to show

its floor, its process and its people owns "trustworthy" before anyone else

thinks to compete for it.

The big idea — "Built to be Trusted" / "ယုံကြည်ရဖို့ တည်ဆောက်ထားတယ်"

Every competitor says quality. We do not say it. We open the doors.

The campaign is one long act of transparency: the factory floor filmed without

staging, the QC bench shown mid-rejection, the line supervisor explaining the

tolerance in her own words, the delivery log published monthly whether it is

good or bad. Trust is not claimed. It is demonstrated, publicly, repeatedly.

Why this and not the obvious one. The obvious campaign is a corporate film

with drone shots, a handshake, and "Quality You Can Trust". It is beautiful, it

is forgettable, and a competitor can copy it in a month. An open factory cannot

be copied by anyone who is not actually confident in their floor — which is the

whole point, and the reason it defends the price premium.

Brand positioning. The supplier you can send your auditor to unannounced.

Key messages.

"Come and see." — an open-door standing invitation, not a campaign line.

"Every batch documented." — QC records issued with delivery, to the buyer's auditors.

"The people who make it." — named operators, not stock photography.

"On time, on record." — delivery performance published monthly, including misses.

Tone of voice. Plain, specific, unhurried. Numbers over adjectives. Burmese

written first (professional register, not colloquial); English transcreated for

Segment C. Never boastful — the evidence carries it.

Hashtags. Primary `#BuiltToBeTrusted` · Secondary `#မြန်မာ့ထုတ်လုပ်မှု` `#OpenFactoryMM`

5. CHANNEL STRATEGY

| Channel | Role | Share |
| --- | --- | --- |
| Facebook | The proof archive — long-form floor content, delivery reports, live Q&A | 40% |
| Viber | The relationship channel — business communities where procurement actually talks | 20% |
| LinkedIn + email | Segment C only — English documentation, capability decks, direct outreach | 15% |
| On-ground | Open Factory Days and two trade fairs — where the deal is actually closed | 20% |
| Trade press / PR | Third-party credibility for the sceptical buyer | 5% |

Facebook and Viber carry Myanmar; LinkedIn carries the region. On-ground closes.

6. CONTENT PLAN

Pillars. The Floor 40% · The Standard 25% · The People 20% · The Record 15%.

| Week | The Floor | The Standard | The People | The Record |
| --- | --- | --- | --- | --- |
| 1–4 | Line walkthrough films (4) | "How we reject a batch" (2) | Operator portraits (3) | Baseline delivery report |
| 5–8 | Raw-material sourcing (2) | Tolerance explainer (2) | Supervisor Q&A live (1) | Month 1 on-time % |
| 9–12 | Capacity under load (2) | Certification walkthrough (2) | Night-shift film (1) | Month 2 + a public miss |
| 13–16 | Customer site visit films (3) | Audit-ready documentation (1) | 10-year staff feature (2) | Quarter summary |

Sample draft — Facebook, Week 2 (Burmese first)

> ဒီအိတ်က ဒီနေ့ ပယ်လိုက်တဲ့ ၁၄ အိတ်ထဲက တစ်အိတ်ပါ။

> အလေးချိန် ၂ ဂရမ် လွဲနေလို့ပါ။ ဖောက်သည်က သတိထားမိမှာ မဟုတ်ပါဘူး။ ဒါပေမဲ့ ကျွန်တော်တို့ သိပါတယ်။

> လာကြည့်ချင်ရင် တံခါးဖွင့်ထားပါတယ်။

>

> *This is one of the 14 bags we rejected today. Two grams outside tolerance.

> The customer would never have noticed. We would have. The door is open — come and see.*

Sample draft — LinkedIn, Week 6 (Segment C)

> Capacity under load, filmed unedited: 11,000 units across a 14-hour shift,

> 0.4% reject rate, full batch documentation issued to the buyer's auditor on

> delivery. The footage is 9 minutes and we have not cut the slow parts out.

> Full QC methodology and certification pack on request.

7. OUTREACH STRATEGY

No consumer influencers. Credibility in B2B comes from three places:

| Tier | Who | Deliverable | Fee band (MMK) |
| --- | --- | --- | --- |
| Authority | 2 industry association figures | Factory visit + honest published assessment | 1,800,000 each |
| Practitioner | 4 procurement/logistics voices | Walkthrough reaction + Viber community post | 700,000 each |
| Customer | 6 existing buyers | Filmed testimonial at *their* site, unscripted | Cost only |

Customer voices outperform everything else in this category and cost the least.

They are also the hardest to fake, which is why buyers believe them.

8. PAID MEDIA PLAN

| Platform | Objective | Budget (MMK) | Audience | Expected |
| --- | --- | --- | --- | --- |
| Facebook | Reach + video views | 9,000,000 | Interest: procurement, wholesale, construction; 28–55; Yangon/Mandalay | CPM 3,500–5,000 |
| Facebook | Lead generation | 7,500,000 | Retargeting 50%+ video viewers | CPL 38,000–52,000 |
| Viber | Community reach | 4,500,000 | Business communities, Yangon commercial | CPM 4,000–6,000 |
| LinkedIn | Segment C reach | 5,000,000 | Sourcing/supply-chain titles, SG/TH/VN | CPC 1,200–2,400 |
| Search | Intent capture | 2,000,000 | "supplier Myanmar", category terms | CPC 700–1,500 |
| **Total** |  | **28,000,000** |  |  |

Sequenced, not simultaneous: reach for 4 weeks builds the retargeting pool that

makes lead generation cheap from week 5. Running both from day one is the most

common and most expensive mistake in this category.

9. ACTIVATION — OPEN FACTORY DAYS

Four Open Factory Days across the campaign, 25–40 buyers each.

Buyers arrive without a curated route. They walk the floor with the supervisor,

watch a live QC rejection, see the documentation system, and leave with a sample

and a batch record carrying their own name on it. No presentation room, no

slides. The factory is the pitch.

Plus presence at two trade fairs (Myanmar Build & Décor, Manufacturing

Myanmar) — a working demonstration bench, not a brochure counter.

10. DETAILED BUDGET

| Line | Unit | Qty | Rate (MMK) | Total (MMK) |
| --- | --- | --- | --- | --- |
| Content production — film crew | day | 12 | 850,000 | 10,200,000 |
| Editing + subtitling (MM/EN) | film | 24 | 220,000 | 5,280,000 |
| Stills + documentation photography | day | 6 | 400,000 | 2,400,000 |
| Paid media (see §8) | — | — | — | 28,000,000 |
| Authority + practitioner fees | — | — | — | 6,400,000 |
| Open Factory Days | event | 4 | 1,850,000 | 7,400,000 |
| Trade fair presence | fair | 2 | 3,200,000 | 6,400,000 |
| English capability pack (design + translation) | pack | 1 | 2,600,000 | 2,600,000 |
| Campaign management (16 weeks) | month | 4 | 2,400,000 | 9,600,000 |
| **Subtotal** |  |  |  | **78,280,000** |
| Contingency 10% |  |  |  | 7,828,000 |
| **Cost base** |  |  |  | **86,108,000** |

11. TIMELINE

| Weeks | Phase | Milestones |
| --- | --- | --- |
| 1–2 | Foundation | Floor audit, QC baseline, crew onboarding, first shoot |
| 3–6 | Proof build | 8 films live, reach campaign, retargeting pool built |
| 5 | Open Factory Day 1 | 25 buyers, first enquiries |
| 7–10 | Demand | Lead-gen campaigns switch on, LinkedIn opens, Fair 1 |
| 9, 13 | Open Factory Days 2–3 | Cumulative 90 buyers on the floor |
| 11–14 | Scale | Customer testimonial films, Fair 2, first delivery report |
| 15–16 | Consolidate | Open Factory Day 4, quarter report, handover |

12. KPIs & SUCCESS METRICS

| Metric | Target | Source |
| --- | --- | --- |
| Qualified enquiries | 120 | CRM, ZYNTH-tagged |
| Cost per qualified lead | ≤ MMK 45,000 | Spend ÷ qualified leads |
| Factory visits booked | 25 | Booking log |
| Open Factory attendance | 120 cumulative | Registration |
| Video completion (Facebook) | ≥ 32% at 30s | Meta |
| Segment C enquiries | 15 | Email + LinkedIn |
| Quote-to-order conversion | +6pp vs baseline | Client sales data |

Baseline must be captured in week 1. Without it, none of these numbers mean

anything at the end — and we will not claim a lift we cannot evidence.

13. ROI PROJECTION

Average first order in this category: MMK 18,000,000. Repeat rate year one: 55%.

| Scenario | Qualified leads | Close rate | New orders | Year-1 revenue (MMK) | Return on 96M |
| --- | --- | --- | --- | --- | --- |
| Conservative | 90 | 8% | 7 | 195,000,000 | 2.0× |
| Base | 120 | 12% | 14 | 391,000,000 | 4.1× |
| Upside | 150 | 16% | 24 | 670,000,000 | 7.0× |

Conservative assumes no Segment C conversion at all and half the expected

factory visits. Even there the campaign returns twice its cost inside a year.

14. RISK & MITIGATION

| Risk | Likelihood | Impact | Mitigation | Owner |
| --- | --- | --- | --- | --- |
| Factory not ready to be filmed honestly | Medium | High | Week-1 floor audit; fix or postpone. We will not stage a clean floor. | ZYNTH + client MD |
| A published delivery miss damages confidence | Medium | Medium | Publish the miss *with* the correction. Buyers forgive the miss and remember the honesty. | ZYNTH |
| Competitor copies the open-factory idea | Low | Low | They must open a floor they are confident in. First mover holds the position. | — |
| Lead volume without lead quality | Medium | High | Qualification criteria agreed week 1; CPL reported against *qualified* only | ZYNTH |
| Staff reluctant to appear on camera | Medium | Medium | Opt-in, paid appearance fee, approval before publication | ZYNTH |

15. ZYNTH FEE & PROFIT MODEL

| Line | MMK |
| --- | --- |
| Cost base (incl. contingency) | 86,108,000 |
| **Client investment at 40% margin** | **143,513,000** |
| ZYNTH gross margin | 57,405,000 (40.0%) |

Clears the 35% floor and sits on the 40% target. Payment: 50% deposit on

signature, 25% at week 8, 25% on final report. Market FX applies. Vendor lines

are RFQ-based and reconciled at actuals — any underspend returns to the client.

If the client's ceiling is lower, the honest reduction is one Open Factory Day

and one trade fair (−MMK 10,600,000 cost base → 125,800,000 investment). We

will not hold the price by cutting the film days, because the films are the

campaign.

16. WHY ZYNTH

We are an AI-run agency, which in this category means one specific thing: we can

produce and publish evidence at a volume a traditional agency prices out of

reach. Twenty-four films in sixteen weeks is not a normal retainer — it is

normal for us.

What we have actually produced, and can show: a 20-section fintech launch

proposal with full audience segmentation and scenario modelling; a premium event

proposal with a complete vendor and risk register; a spec product film built to

commercial sound-design standards; eight 3D stage and exhibition concepts.

What we do not claim: manufacturing case studies. This would be our first in the

sector, and we would rather say so than invent one. What we bring is the method

and the production capacity — the floor is the client's, and it is the proof.

---

*ZYNTH — The Intelligence of Creativity · zynth.asia*

*Figures indicative, vendor lines subject to RFQ. Market FX. 50% deposit on signature.*

Prepared by ZYNTH. Figures are indicative and subject to vendor RFQ. Market FX applies. 50% deposit on signature.