ZYNTH  |  Myanmar-First Bilingual Production System

# Last Mile Ledger

နောက်ဆုံးမိုင်ကို ရှင်းလင်းစေမယ့် Last Mile Ledger

CAMPAIGN / ACTIVATION PROPOSAL  •  CMP-2026-LOGISTICS-02  •  Logistics / Myanmar

Client-ready planning proposal. All client, customer, carrier, fleet, route, port, warehouse, data, price, capacity, safety, permit, rights, partner and performance elements are proposed/TBC until written approval.

# 1. Commercial Brief

စီးပွားရေးဆိုင်ရာ အကျဉ်းချုပ်

| Format | SME route-visibility retail and merchant activation |
| --- | --- |
| Commercial tension | Small merchants need a practical conversation about deliveries, returns and customer communication without being sold an unverified service promise. |
| Objective | Move from informal delivery frustration to a client-approved merchant consultation. |
| Audience | SME owners and e-commerce operators who need to frame delivery experience requirements. |
| Creative territory | Every Stop Leaves a Clearer Story |
| Seasonal / date logic | Proposed for an early October 2026 SME planning window, with public-holiday operating suitability TBC. |

# 2. Conversion Experience

ပြောင်းလဲမှု အတွေ့အကြုံ

| Conversion mechanism | A paper 'last-mile ledger' lets merchants prioritise notification, handover or returns questions and book a consented consultation. |
| --- | --- |
| Experience flow | 1) Notice the decision tension 2) Work through a controlled fictional scenario 3) Identify a next question and accountable owner 4) Give consent for a client-approved discovery conversation. |

# 3. Proposed Workplan

အဆိုပြုလုပ်ငန်းစဉ်

| Stage | Indicative timing | ZYNTH output | Client decision required |
| --- | --- | --- | --- |
| G0–G1: Brief & evidence | Working days 1–2 | Evidence register, audience hypothesis, operational/claim boundary | Approve objective, data boundary and factual service/product context |
| G2–G3: Strategy & creative | Working days 3–5 | Journey, creative route, experience/content plan | Select route and priority conversion action |
| G4: Feasibility | Working days 6–8 | Safety, route/site, privacy, rights, staffing and risk register | Name accountable owners and clear go/no-go conditions |
| G5: Production readiness | Working days 9–12 | Run-of-show, asset list, training, capture and escalation plan | Approve final assets, rules, terms and operations |
| G6–G7: Live & learn | Client/site-confirmed | Dashboard check, daily log, decision record and learning note | Approve optimisation or close-out |

# 4. Budget Envelope

ဘတ်ဂျက် စီမံကိန်း

| Planning scenario | Non-tax envelope | Use |
| --- | --- | --- |
| Lean | MMK 9.6m | Minimum viable controlled pilot |
| Recommended | MMK 19.4m | Balanced production, operations and learning capacity |
| Flagship | MMK 39.8m | Expanded route, content and operational capacity |

| Recommended budget workstream | Indicative share | Planning amount |
| --- | --- | --- |
| Strategy, creative & project direction | 15% | MMK 2.9m |
| Experience/production operations | 34% | MMK 6.6m |
| Staffing, training & facilitation | 18% | MMK 3.5m |
| Data, CRM & reporting | 12% | MMK 2.3m |
| Safety, route/site and guest operations | 11% | MMK 2.1m |
| Contingency | 10% | MMK 1.9m |

# 5. Measurement and Commercial Scenarios

စောင့်ကြည့်တိုင်းတာမှုနှင့် Scenario

| Scenario | Directional outcome |
| --- | --- |
| Conservative | 18 merchant cards / 4 consultations |
| Base | 38 merchant cards / 10 consultations |
| Upside | 70 merchant cards / 20 consultations |

| Primary KPIs | merchant priority cards; consented consultations; return-journey briefs |
| --- | --- |
| Data rule | Capture only client-approved, consented data needed for a stated follow-up. Do not display or collect real shipment, customer, employee, route, fleet, cargo or commercial-confidential data. |
| Scenario rule | Planning assumptions only. Replace with client funnel, margin, service capacity, route, inventory and attribution data before commercial sign-off. |

# 6. Mandatory Preflight

မဖြစ်မနေ အတည်ပြုရမည့်အချက်များ

merchant eligibility

privacy notice

brand/merchant permissions

follow-up process

No price, transit time, delivery, capacity, customs, safety, security, tracking, emissions, route, warehouse, carrier, port, employment, service-level or partnership claim may be used without written client/legal approval.

All third-party visual, location, vehicle, person, uniform, system-interface, music, talent and photography rights must be cleared before production.

# 7. Evidence and Use Limits

အထောက်အထားနှင့် အသုံးပြုခွင့် ကန့်သတ်ချက်

| ID | Public source | URL |
| --- | --- | --- |
| LOG-S01 | Myanmar Logistics Institute / MIFFA | https://myanmarlogisticsinstitute.com/ |
| LOG-S02 | EuroCham Myanmar — Logistics Briefing | https://eurocham-myanmar.org/events/logistics-briefing-current-global-trade-transport-insights-for-businesses-in-myanmar/ |

Evidence use: sources provide public logistics, trade, transport, capability and calendar context only. They do not validate any future commercial partnership, venue, route, carrier, capacity, performance, attendance, lead or sales outcome.

Prepared by Manus AI for ZYNTH. Planning document only; not a contract, supplier quotation, legal advice, safety clearance, route plan or operational approval.