ZYNTH  |  Myanmar-First Bilingual Production System

# Route Before Rush

အလျင်မတက်ခင် လမ်းကြောင်းစဉ်းစားမယ့် Route Before Rush

CAMPAIGN / ACTIVATION PROPOSAL  •  CMP-2026-LOGISTICS-04  •  Logistics / Myanmar

Client-ready planning proposal. All client, customer, carrier, fleet, route, port, warehouse, data, price, capacity, safety, permit, rights, partner and performance elements are proposed/TBC until written approval.

# 1. Commercial Brief

စီးပွားရေးဆိုင်ရာ အကျဉ်းချုပ်

| Format | executive demand-planning forum |
| --- | --- |
| Commercial tension | Business leaders can defer capacity and coordination decisions until a peak period makes the conversation harder. |
| Objective | Move from reactive planning to a named, client-approved route and coordination session. |
| Audience | Commercial, operations and procurement leaders responsible for a client-defined seasonal or promotional period. |
| Creative territory | Plan the Rush Before It Plans You |
| Seasonal / date logic | Proposed for Q4 2026 planning, with holiday dates used only as calendar guardrails and client demand assumptions TBC. |

# 2. Conversion Experience

ပြောင်းလဲမှု အတွေ့အကြုံ

| Conversion mechanism | A facilitated 'decision window' board captures non-sensitive planning questions and offers an executive follow-up session. |
| --- | --- |
| Experience flow | 1) Notice the decision tension 2) Work through a controlled fictional scenario 3) Identify a next question and accountable owner 4) Give consent for a client-approved discovery conversation. |

# 3. Proposed Workplan

အဆိုပြုလုပ်ငန်းစဉ်

| Stage | Indicative timing | ZYNTH output | Client decision required |
| --- | --- | --- | --- |
| G0–G1: Brief & evidence | Working days 1–2 | Evidence register, audience hypothesis, operational/claim boundary | Approve objective, data boundary and factual service/product context |
| G2–G3: Strategy & creative | Working days 3–5 | Journey, creative route, experience/content plan | Select route and priority conversion action |
| G4: Feasibility | Working days 6–8 | Safety, route/site, privacy, rights, staffing and risk register | Name accountable owners and clear go/no-go conditions |
| G5: Production readiness | Working days 9–12 | Run-of-show, asset list, training, capture and escalation plan | Approve final assets, rules, terms and operations |
| G6–G7: Live & learn | Client/site-confirmed | Dashboard check, daily log, decision record and learning note | Approve optimisation or close-out |

# 4. Budget Envelope

ဘတ်ဂျက် စီမံကိန်း

| Planning scenario | Non-tax envelope | Use |
| --- | --- | --- |
| Lean | MMK 15.6m | Minimum viable controlled pilot |
| Recommended | MMK 32.2m | Balanced production, operations and learning capacity |
| Flagship | MMK 65.6m | Expanded route, content and operational capacity |

| Recommended budget workstream | Indicative share | Planning amount |
| --- | --- | --- |
| Strategy, creative & project direction | 15% | MMK 4.8m |
| Experience/production operations | 34% | MMK 10.9m |
| Staffing, training & facilitation | 18% | MMK 5.8m |
| Data, CRM & reporting | 12% | MMK 3.9m |
| Safety, route/site and guest operations | 11% | MMK 3.5m |
| Contingency | 10% | MMK 3.2m |

# 5. Measurement and Commercial Scenarios

စောင့်ကြည့်တိုင်းတာမှုနှင့် Scenario

| Scenario | Directional outcome |
| --- | --- |
| Conservative | 10 executive seats / 3 planning sessions |
| Base | 22 executive seats / 7 planning sessions |
| Upside | 40 executive seats / 13 planning sessions |

| Primary KPIs | decision-window participation; named planning sessions; approved next-step briefs |
| --- | --- |
| Data rule | Capture only client-approved, consented data needed for a stated follow-up. Do not display or collect real shipment, customer, employee, route, fleet, cargo or commercial-confidential data. |
| Scenario rule | Planning assumptions only. Replace with client funnel, margin, service capacity, route, inventory and attribution data before commercial sign-off. |

# 6. Mandatory Preflight

မဖြစ်မနေ အတည်ပြုရမည့်အချက်များ

client demand assumptions

executive invite list

data boundaries

facilitation plan

No price, transit time, delivery, capacity, customs, safety, security, tracking, emissions, route, warehouse, carrier, port, employment, service-level or partnership claim may be used without written client/legal approval.

All third-party visual, location, vehicle, person, uniform, system-interface, music, talent and photography rights must be cleared before production.

# 7. Evidence and Use Limits

အထောက်အထားနှင့် အသုံးပြုခွင့် ကန့်သတ်ချက်

| ID | Public source | URL |
| --- | --- | --- |
| LOG-S02 | EuroCham Myanmar — Logistics Briefing | https://eurocham-myanmar.org/events/logistics-briefing-current-global-trade-transport-insights-for-businesses-in-myanmar/ |
| LOG-S06 | Myanmar Government — Upcoming Holidays | https://myanmar.gov.mm/upcoming-holidays/ |

Evidence use: sources provide public logistics, trade, transport, capability and calendar context only. They do not validate any future commercial partnership, venue, route, carrier, capacity, performance, attendance, lead or sales outcome.

Prepared by Manus AI for ZYNTH. Planning document only; not a contract, supplier quotation, legal advice, safety clearance, route plan or operational approval.