ZYNTH  |  Myanmar-First Bilingual Production System

# The Resilience Desk

အနှောင့်အယှက်ကို စီမံမယ့် Resilience Desk

CAMPAIGN / ACTIVATION PROPOSAL  •  CMP-2026-LOGISTICS-10  •  Logistics / Myanmar

Client-ready planning proposal. All client, customer, carrier, fleet, route, port, warehouse, data, price, capacity, safety, permit, rights, partner and performance elements are proposed/TBC until written approval.

# 1. Commercial Brief

စီးပွားရေးဆိုင်ရာ အကျဉ်းချုပ်

| Format | account-based disruption decision sprint and CRM reactivation |
| --- | --- |
| Commercial tension | Past customer conversations can stall when leaders face disruption, changing priorities or unclear next decisions. |
| Objective | Move from dormant conversation to an explicit re-scope, defer or discovery-decision meeting. |
| Audience | Client-owned, consented B2B contacts only; no outreach occurs until the client confirms data rights and messaging. |
| Creative territory | When the Route Changes, the Conversation Can Continue |
| Seasonal / date logic | Proposed for December 2026 account-planning, avoiding public-holiday communication dates unless the client confirms suitability. |

# 2. Conversion Experience

ပြောင်းလဲမှု အတွေ့အကြုံ

| Conversion mechanism | A three-option decision message routes consented contacts to a client-approved decision sprint; no service-continuity promise is made. |
| --- | --- |
| Experience flow | 1) Notice the decision tension 2) Work through a controlled fictional scenario 3) Identify a next question and accountable owner 4) Give consent for a client-approved discovery conversation. |

# 3. Proposed Workplan

အဆိုပြုလုပ်ငန်းစဉ်

| Stage | Indicative timing | ZYNTH output | Client decision required |
| --- | --- | --- | --- |
| G0–G1: Brief & evidence | Working days 1–2 | Evidence register, audience hypothesis, operational/claim boundary | Approve objective, data boundary and factual service/product context |
| G2–G3: Strategy & creative | Working days 3–5 | Journey, creative route, experience/content plan | Select route and priority conversion action |
| G4: Feasibility | Working days 6–8 | Safety, route/site, privacy, rights, staffing and risk register | Name accountable owners and clear go/no-go conditions |
| G5: Production readiness | Working days 9–12 | Run-of-show, asset list, training, capture and escalation plan | Approve final assets, rules, terms and operations |
| G6–G7: Live & learn | Client/site-confirmed | Dashboard check, daily log, decision record and learning note | Approve optimisation or close-out |

# 4. Budget Envelope

ဘတ်ဂျက် စီမံကိန်း

| Planning scenario | Non-tax envelope | Use |
| --- | --- | --- |
| Lean | MMK 7.2m | Minimum viable controlled pilot |
| Recommended | MMK 14.9m | Balanced production, operations and learning capacity |
| Flagship | MMK 30.5m | Expanded route, content and operational capacity |

| Recommended budget workstream | Indicative share | Planning amount |
| --- | --- | --- |
| Strategy, creative & project direction | 15% | MMK 2.2m |
| Experience/production operations | 34% | MMK 5.1m |
| Staffing, training & facilitation | 18% | MMK 2.7m |
| Data, CRM & reporting | 12% | MMK 1.8m |
| Safety, route/site and guest operations | 11% | MMK 1.6m |
| Contingency | 10% | MMK 1.5m |

# 5. Measurement and Commercial Scenarios

စောင့်ကြည့်တိုင်းတာမှုနှင့် Scenario

| Scenario | Directional outcome |
| --- | --- |
| Conservative | 12 re-engagement responses / 2 meetings |
| Base | 28 re-engagement responses / 7 meetings |
| Upside | 52 re-engagement responses / 14 meetings |

| Primary KPIs | consented responses; decision meetings; explicit re-scope/defer outcomes |
| --- | --- |
| Data rule | Capture only client-approved, consented data needed for a stated follow-up. Do not display or collect real shipment, customer, employee, route, fleet, cargo or commercial-confidential data. |
| Scenario rule | Planning assumptions only. Replace with client funnel, margin, service capacity, route, inventory and attribution data before commercial sign-off. |

# 6. Mandatory Preflight

မဖြစ်မနေ အတည်ပြုရမည့်အချက်များ

CRM data rights

message approval

privacy/opt-out language

sales ownership

No price, transit time, delivery, capacity, customs, safety, security, tracking, emissions, route, warehouse, carrier, port, employment, service-level or partnership claim may be used without written client/legal approval.

All third-party visual, location, vehicle, person, uniform, system-interface, music, talent and photography rights must be cleared before production.

# 7. Evidence and Use Limits

အထောက်အထားနှင့် အသုံးပြုခွင့် ကန့်သတ်ချက်

| ID | Public source | URL |
| --- | --- | --- |
| LOG-S02 | EuroCham Myanmar — Logistics Briefing | https://eurocham-myanmar.org/events/logistics-briefing-current-global-trade-transport-insights-for-businesses-in-myanmar/ |
| LOG-S06 | Myanmar Government — Upcoming Holidays | https://myanmar.gov.mm/upcoming-holidays/ |

Evidence use: sources provide public logistics, trade, transport, capability and calendar context only. They do not validate any future commercial partnership, venue, route, carrier, capacity, performance, attendance, lead or sales outcome.

Prepared by Manus AI for ZYNTH. Planning document only; not a contract, supplier quotation, legal advice, safety clearance, route plan or operational approval.